## 📋 Feature Registry
MF ADVISOR — FEATURE REGISTRY
v6.9 · 2026-07-21 · 163 features · 100% open-source · no API keys · no subscription · local-first persistence
ID | Category | Feature | Status | Priority | Ver Added | Target | Effort | Description | Notes / Why
F001 | Data Import | CAMS CAS .xls import | Completed | High | v5.0 | v5.0 | M | Parse CAMS Consolidated Account Statement .xls | parseXLS() present. Core parser working.
F002 | Data Import | Folio separator row fix | Completed | High | v5.273 | v5.273 | S | Skip '--' separator rows in multi-folio CAS imports | FIXED v5.273: rawBalCheck/rawMVCheck guard re-added to parseXLS().
F003 | Data Import | CAMS Transaction XLSX import | Completed | High | — | v5.276 | M | Import newer CAMS XLSX export format | DONE v5.276: parseCAMSXlsxRows. Auto-detected via detectFormat().
F004 | Data Import | CAMS Current Value XLSX import | Completed | Medium | — | v5.281 | M | Verify multi-folio balances via CAMS CV export | DONE v5.281: parseCAMSCurrentValue() auto-detects CAMS Current Value XLSX via cams_cv format code. Seeds holdings as snapshot rows. Wire through parseAnyFile.
F005 | Data Import | KFintech XLSX import | Completed | Medium | — | v5.276 | M | Import KFintech transaction exports directly | DONE v5.276: parseKFintechRows. Auto-detected via detectFormat().
F006 | Data Import | Generic CSV import | Completed | Low | — | v5.276 | S | Fallback CSV parser for any tabular export | DONE v5.276: parseGenericCSV. Handles Date/Scheme/Type CSV.
F007 | Data Import | Auto format detection | Completed | Medium | — | v5.276 | S | Auto-detect CAMS/KFintech/CSV format from headers | DONE v5.276: parseAnyFile routes by extension + header detection.
F008 | Data Import | Incremental XLS append (dedup) | Completed | High | v5.273 | v5.273 | S | Append new transactions from XLS without duplicates | FIXED v5.273: appendXLS callback + Append XLS button in Data Management.
F009 | Data Import | Bulk upload transactions CSV | Completed | Medium | v5.272 | v5.272 | M | Upload CSV of transactions with deduplication | bulkUploadTransactionsCSV present.
F010 | Data Import | JSON backup export & import | Completed | High | v5.0 | v5.0 | M | Full backup/restore including NAV cache and settings | saveToJSON and loadFromFile both working.
F011 | Data Import | Folder/directory auto-save | Completed | Medium | v5.1 | v5.1 | L | Auto-save to user-chosen folder on every change | File System Access API. Chrome/Edge only.
F012 | Scheme Mapping | Auto-map via ISIN | Completed | High | v5.0 | v5.0 | M | Use ISIN for fast accurate fund identification | ISIN lookup against AMFI master.
F013 | Scheme Mapping | AMC locking in matchScore | Completed | Critical | v5.272 | v5.272 | M | Prevent cross-AMC mismatches (ABSL→Edelweiss etc) | AMC_LOCK table. Fixed 7 wrong mappings.
F014 | Scheme Mapping | ABSL search query expansion | Completed | High | v5.272 | v5.272 | S | Expand ABSL prefix before MFAPI search | Prevents wrong AMC results for ABSL funds.
F015 | Scheme Mapping | Inline edit — Search & Pick | Completed | High | v5.272 | v5.272 | L | Per-row live search dropdown in Settings | smEditRow/smEditSearch/smEditPick working.
F016 | Scheme Mapping | Stale NAV cleared on remap | Completed | High | v5.272 | v5.272 | S | Delete old wrong NAV immediately on remap | smEditPick deletes navByScheme before re-fetch.
F017 | Scheme Mapping | Name confirmed from MFAPI | Completed | Medium | v5.272 | v5.272 | S | Update amfiName from MFAPI meta after each pick | d.meta.scheme_name used on every pick/apply.
F018 | Scheme Mapping | Per-row re-fetch NAV (⟳) | Completed | Medium | v5.272 | v5.272 | S | Re-fetch NAV and confirm name for one scheme | ⟳ button per row in Scheme Mapping table.
F019 | Scheme Mapping | Refresh All NAV | Completed | Medium | v5.272 | v5.272 | S | Clear and re-fetch NAV for all mapped schemes | Refresh All NAV button in Scheme Mapping card.
F020 | Scheme Mapping | Bulk upload mapping CSV | Completed | High | v5.272 | v5.272 | M | Upload CSV of Scheme Name/AMFI Code in bulk | bulkUploadSchemeMapping. Clears and re-fetches NAV.
F021 | Scheme Mapping | Skip exited funds | Completed | Medium | — | v5.276 | S | Auto-skip zero-unit schemes; 'skip (exited)' button | DONE v5.276: Skip (exited) button; wrapped in Fragment to fix adjacent JSX crash.
F022 | Multi-Currency | FMT() replaces INR() everywhere | Completed | Critical | v5.273 | v5.273 | L | All monetary values respect selected currency | FIXED v5.273: All 55 INR() calls replaced with FMT(). Dashboard, FY Summary, XIRR Review, NPV, Fund Overview now fully currency-aware.
F023 | Multi-Currency | Currency selector UI | Completed | Medium | v5.1 | v5.1 | S | Currency toggle in header and Settings | Buttons update G_CURRENCY correctly.
F024 | Multi-Currency | Display unit (Cr/L/K) | Completed | Low | v5.1 | v5.1 | S | Toggle between Crores/Lakhs/thousands | G_UNIT and DISPLAY_UNITS respected by FMT().
F025 | Dashboard | Portfolio value KPI card | Completed | Critical | v5.273 | v5.273 | S | Hero card shows current portfolio value in selected currency | FIXED v5.273: INR()→FMT(). Currency switch now works.
F026 | Dashboard | Unrealised gain KPI card | Completed | High | v5.273 | v5.273 | S | Hero card shows unrealised gain in selected currency | FIXED v5.273: INR()→FMT().
F027 | Dashboard | Invested / Net deployed cards | Completed | High | v5.273 | v5.273 | S | Hero cards in selected currency | FIXED v5.273: INR()→FMT() on both cards.
F028 | Dashboard | Portfolio timeline chart | Completed | High | v5.0 | v5.0 | L | Area/line chart corpus vs benchmarks over time | Working. Y-axis labels now use FMT().
F029 | Dashboard | Top 5 / Bottom 5 by XIRR | Completed | Medium | v5.0 | v5.0 | M | Ranked fund cards by XIRR | Fund values now use FMT().
F030 | Dashboard | Portfolio recommendations | Completed | Medium | v5.0 | v5.0 | L | Rules-based recommendations using XIRR/Sharpe/Alpha | Working.
F031 | Dashboard | FY Summary collapsible card | Completed | Low | v5.2 | v5.2 | M | FY breakdown accessible from Dashboard | CollapsibleCard present.
F032 | Dashboard | NAV date in portfolio value card | Completed | Low | — | v5.275 | S | Show exact NAV date in portfolio value card sub-label | DONE v5.275: navAsOf() shows 'NAV current' or 'NAV N days old' in Portfolio Value card sub-label.
F033 | Analysis | Fund Overview table | Completed | High | v5.0 | v5.0 | L | Filterable table with full fund metrics | All monetary columns now use FMT().
F034 | Analysis | Fund Performance page | Completed | High | v5.0 | v5.0 | L | Per-fund NAV % return vs benchmarks | Working.
F035 | Analysis | FY Summary page — currency | Completed | High | v5.273 | v5.273 | M | All FY Summary monetary values in selected currency | FIXED v5.273: 19 INR()→FMT() in FYSummaryPage.
F036 | Analysis | XIRR Review — currency | Completed | High | v5.273 | v5.273 | M | XIRR Review chart and table in selected currency | FIXED v5.273: INR()→FMT() in XirrReviewPage and XIRRHistoryChart.
F037 | Analysis | Analysis page (Sharpe/Beta/Alpha) | Completed | High | v5.0 | v5.0 | L | Risk-adjusted metrics with rolling calculations | Working.
F038 | Analysis | NPV page — currency | Completed | Medium | v5.273 | v5.273 | M | NPV table and chart in selected currency | FIXED v5.273: INR()→FMT() in NpvPage.
F039 | Analysis | Validation panel | Completed | High | v5.273 | v5.273 | M | Check duplicates, missing NAV, future dates, NAV mismatch | FIXED v5.273: runValidation (6 rules) + 🔍 button in Data Management + filterable results panel with Dismiss/Re-run.
F040 | Analysis | Group by AMC/class/status | Completed | Medium | v5.272 | v5.272 | M | Group fund rows in Overview and Performance | groupBy lifted to App, DataTable supports headers.
F041 | Analysis | Show/hide exited funds (filter) | Completed | High | v5.273 | v5.273 | S | Exited fund toggle filters all page calculations | FIXED v5.273: filteredEnabledSet useMemo added in App. Passed to all 7 page components instead of raw enabledSet.
F042 | Analysis | Multi-portfolio compare page | Completed | Low | — | v5.282 | XL | Side-by-side value/XIRR/gain across portfolios | DONE v5.282: PortfolioComparePage — tab auto-appears when 2+ portfolios. Cards + table. Respects returnBasis. Loads from _store without switching.
F043 | Help & Docs | Help page structure | Completed | Medium | v5.2 | v5.2 | M | 4-tab help page: FAQ, User Manual, Technical, Changelog | Structure present and working.
F044 | Help & Docs | FAQ content | Completed | Medium | v5.2 | v5.2 | M | Answers to common user questions | 10 FAQ entries.
F045 | Help & Docs | User Manual content | Completed | Medium | v5.2 | v5.276 | M | Step-by-step guides for all features | DONE v5.276: Getting Started + Settings sections updated.
F046 | Help & Docs | Technical reference / formulas | Completed | Low | v5.2 | v5.276 | L | Formula documentation for XIRR, Sharpe, Alpha etc | DONE v5.276: Glossary of Terms added to Technical tab (12 definitions).
F047 | Help & Docs | Changelog in Help page | Completed | Low | v5.2 | v5.276 | S | Version history | DONE v5.276: Changelog entries for v5.276, v5.275, v5.274, v5.273.
F048 | Help & Docs | Cross-links Help↔Settings | Completed | Low | — | v5.276 | S | Links from Help to relevant Settings sections | DONE v5.276: Getting Help section with cross-links added.
F049 | Settings | Dataset status banner | Completed | Medium | v5.272 | v5.272 | S | Txn/scheme/mapped/NAV counts at top of Settings | Working.
F050 | Settings | Header transaction chip | Completed | Low | v5.272 | v5.272 | S | Live txn count in app header | Working.
F051 | Settings | Clear & New Analysis (confirm) | Completed | Medium | v5.272 | v5.272 | S | Confirm dialog before wiping all data | Working.
F052 | Settings | Add Transaction + NAV auto-fetch | Completed | Medium | v5.272 | v5.272 | S | Auto-fetch NAV after Add Transaction | Working.
F053 | Settings | Scheme Mapping review table | Completed | High | v5.272 | v5.272 | L | Full inline-edit table with search, re-fetch, clear | Working.
F054 | Settings | Append XLS Transactions button | Completed | High | v5.273 | v5.273 | S | Append XLS button in Data Management | FIXED v5.273: appendXLS callback + button added.
F055 | NAV | NAV auto-refresh interval | Completed | Medium | v5.0 | v5.0 | M | Configurable background refresh of latest NAV | Working.
F056 | NAV | NAV staleness date display | Completed | Low | — | v5.275 | S | Exact NAV date in portfolio value card | DONE v5.275: navAsOf() covers staleness. Portfolio Value sub-label updates dynamically.
F057 | NAV | lastBusinessDay NAV cap | Completed | Medium | v5.272 | v5.272 | S | Cap period end to last business day | lastBusinessDay() present.
F058 | NAV | Benchmark comparison | Completed | High | v5.0 | v5.0 | L | Nifty 50 and custom benchmarks vs portfolio | Working.
F059 | NAV | PPF equivalent benchmark | Completed | Medium | v5.0 | v5.0 | M | Synthetic PPF corpus from same cash flows | Working.
F060 | UX | Multi-user profiles | Completed | Medium | v5.1 | v5.1 | L | Separate saved states per user | Working.
F061 | UX | Period picker (1M–All) | Completed | High | v5.0 | v5.0 | S | Period filter shared across all pages | Working.
F062 | UX | Export HTML / Word / Print | Completed | Medium | v5.1 | v5.1 | L | Full report export | Working.
F063 | UX | PWA installable | Completed | Low | v5.1 | v5.1 | M | Add to Home Screen on Android/iOS | Working.
F064 | UX | Edge Tracking Prevention fix | Completed | Critical | v5.272 | v5.272 | M | Works in Edge when localStorage blocked | _store wrapper with memory fallback.
F065 | UX | Loading screen Start Fresh | Completed | High | v5.272 | v5.272 | S | 5s safety timeout + escape button | Prevents permanent blank screen.
F066 | UX | Term definitions glossary | Completed | Low | v5.0 | v5.276 | M | 15 metric definitions in Fund Overview | DONE v5.276: Glossary accessible from Technical tab in Help.
F067 | UX | Multi-portfolio system | Completed | Low | — | v5.281 | XL | Multiple named portfolio profiles | DONE v5.281: Users renamed to Portfolios throughout — header badge, Portfolio Manager modal, add/delete/switch copy, default name.
F068 | UX | Root-level error boundary | Completed | Medium | — | v5.275 | S | Catch App-level crashes gracefully | DONE v5.275: RootErrorBoundary class wraps createRoot(). App crashes show error + Reload button.
F069 | UX | Blank screen prevention | Completed | Critical | v5.272 | v5.273 | L | No Babel parse errors, no literal newlines in JS | Fixed multiple issues across v5.272-273.
F070 | Display Format | Flexible format engine (applyFMT/customFmt) | Completed | Critical | v5.274 | v5.274 | L | Full format engine replacing old FMT(). Currency×rate, auto/manual scale, decimals 0-4, neg style, separator, zero display. | FIXED v5.274: applyFMT() reads G_FMT global. customFmt() parses Excel-style strings. Old duplicate FMT/G_CURRENCY declarations removed — was the blank-screen cause.
F071 | Display Format | Format presets (6 one-click) | Completed | High | v5.274 | v5.274 | S | 6 presets: ₹ Auto, ₹ Lakhs, ₹ Crores, ₹ Full, $ Millions, € Millions. | FIXED v5.274: FMT_PRESETS array. Clicking a preset calls applyDisplayFmt() syncing state + G_FMT global.
F072 | Display Format | Live preview in Settings | Completed | High | v5.274 | v5.274 | S | Shows formatted output of ₹1,23,45,678.50 updating instantly as controls change. | FIXED v5.274: Preview row in format panel calls applyFMT(12345678.5, displayFmt) reactively.
F073 | Display Format | Fine controls: currency, scale, decimals, neg, sep, zero | Completed | High | v5.274 | v5.274 | M | 6 independent controls in 3-column grid. All update displayFmt state and G_FMT global immediately. | FIXED v5.274: Currency+Scale as dropdowns, Decimals/Neg/Thousands/Zero as pill button groups.
F074 | Display Format | Custom format string (Excel-style) | Completed | High | v5.274 | v5.274 | M | Custom format string shown when scale=custom. Parses prefix+#,##0.00+suffix pattern. | FIXED v5.274: customFmt() supports ₹#,##0.00, #,##0 Cr, (#,##0), etc.
F075 | Display Format | Editable exchange rates | Completed | Medium | v5.274 | v5.274 | S | User enters own FX rates (1 INR=X) for USD/EUR/GBP/AED/SGD in collapsible section. | FIXED v5.274: Rates stored in displayFmt.rates. applyFMT reads rates[currency] first, falls back to CURRENCIES[].rate.
F076 | Display Format | SGD and GBP added | Completed | Low | v5.274 | v5.274 | S | Singapore Dollar and British Pound added. Total 6 currencies: INR, USD, EUR, GBP, AED, SGD. | FIXED v5.274: CURRENCIES object extended.
F077 | Display Format | Header format badge (replaces dropdown) | Completed | Medium | v5.274 | v5.274 | S | Compact badge shows current format (e.g. ₹.00 or $M.00). Clicking opens Settings. | FIXED v5.274: Old <select> replaced with <button> showing sym+scale+decimals pattern.
F078 | Display Format | displayFmt persisted in JSON backup | Completed | Medium | v5.274 | v5.274 | S | All format settings saved in JSON backup and restored correctly on load. | FIXED v5.274: displayFmt in saveState. Restore sets state + G_FMT/G_CURRENCY/G_UNIT globals.
F079 | Bug Fix | Duplicate FMT/G_CURRENCY/G_UNIT declarations removed | Completed | Critical | v5.274 | v5.274 | S | Blank screen caused by duplicate function FMT( and let G_CURRENCY= in v5.274 output. | ROOT CAUSE: new format infrastructure was ADDED on top of old block instead of replacing it. Fix: start from v5.273 clean base, replace old block in one shot, verify count=1 before deploy.
F080 | Bug Fix | displayFmt not in SettingsPage signature (blank/crash) | Completed | Critical | v5.274 | v5.274 | S | Settings page crashed with 'ReferenceError: displayFmt is not defined'. | ROOT CAUSE: deployed v5.274.html was an intermediate build — displayFmt/applyDisplayFmt were in the App call-site but NOT in SettingsPage's destructured props signature. Fix: deployed from the correct working file with both in the signature.
F081 | NAV | Incremental NAV fetch (skip current, append missing only) | Completed | High | v5.274 | v5.274 | M | Fetch only missing NAV dates instead of re-downloading full history on every refresh. | v5.274: fetchNavBackground now: (1) skips schemes whose last NAV date ≥ last business day (zero API calls); (2) uses /mf/{code}/latest for stale schemes that have existing data — appends only new entries; (3) falls back to full /mf/{code} only when no data exists. Logs 'NAV: N updated, M already current' to console.
F082 | NAV | Separate NAV cache (mfa_nav_v1_{user}) | Completed | High | v5.275 | v5.275 | M | NAV history stored in its own _store key — removed from main state blob. | v5.275: saveNavCache/loadNavCache helpers. Startup loads from cache key first. Auto-persists on navByScheme state change. Cleared on reset and user-switch.
F083 | NAV | Parallel NAV fetch (5 concurrent) | Completed | High | v5.275 | v5.275 | M | 5 schemes fetched concurrently via Promise.all — ~5x faster than sequential. | v5.275: fetchOne() per scheme, batched Promise.all(CONCURRENCY=5). UI and cache flushed after each batch for live progress.
F084 | NAV | Incremental NAV (/latest endpoint) | Completed | High | v5.275 | v5.275 | S | Stale schemes use /mf/{code}/latest (small payload) instead of full re-download. | v5.275: Three tiers — skip current, /latest if stale with data, full fetch if empty. 95%+ less data on daily refreshes.
F085 | UX | Root-level error boundary | Completed | Medium | v5.275 | v5.275 | S | App-level crashes show error panel + Reload button instead of blank screen. | v5.275: RootErrorBoundary class component. Wraps ReactDOM.createRoot render. Uses _store.remove not localStorage on reload.
F086 | Bug Fix | returnBasis not in DashboardPage scope — blank screen fix | Completed | Critical | v5.277 | v5.277 | S | returnBasis was used inside DashboardPage JSX but never declared in its props — ReferenceError at render. | ROOT CAUSE: Changes were applied to file but DashboardPage signature + call site were not updated together. Fix: start from v5.276 clean base, apply all 13 changes atomically with assertion checks before saving.
F087 | Analysis | Return basis selector (Book Cost / Net Deployed / Gross Invested) | Completed | High | v5.277 | v5.277 | M | Toggle on Dashboard above hero cards and in Settings → Display Format. Default: Book Cost (FIFO). | v5.277: returnBasis state in App. Passed to DashboardPage (sig + call) and SettingsPage (sig + call). Persisted in JSON backup. Restored on load.
F088 | Analysis | heroStats: all three gain bases computed every render | Completed | High | v5.277 | v5.277 | M | gain_net, gain_book, gain_gross and matching gainPct always available. | v5.277: totalBookCost = sum of FIFO costBasis across all enabled schemes. gain=returnBasis determines which value is the primary 'gain' shown. returnBasis in useMemo deps.
F089 | Dashboard | Hero cards expanded: 6 cards showing all perspectives | Completed | High | v5.277 | v5.277 | S | Portfolio Value, Gross Invested, Redeemed, Net Deployed, Book Cost (FIFO), Gain vs selected basis. | v5.277: Old 3-card layout (Invested, Net Deployed, Unrealised Gain) replaced. Gain card label is dynamic: 'Gain vs Book Cost' / 'Gain vs Net Deployed' / 'Gain vs Gross Invested'.
F090 | Settings | Return Calculation Basis explanation in Settings | Completed | Medium | v5.277 | v5.277 | S | Plain-language description of all three bases in Settings → Display Format card. | v5.277: Section added below Exchange Rates expander. Explains why Net Deployed can mislead.
F091 | Analysis | Fund Overview: returnBasis-aware Abs Return % | Completed | High | v5.278 | v5.278 | M | Abs Return % denominator changes with return basis: Book Cost, Net Deployed, or Gross Invested. | v5.278: rpDenom computed from returnBasis in FundOverview per-fund loop and totals row. Column header updates dynamically: 'Abs Return % (vs Book Cost)' etc. returnBasis passed via prop. ¦ v5.285: returnBasis now correctly passed in FundOverviewPage JSX call (was missing from call site).
F092 | Analysis | fundStats: costBasis, returnPct, unrealisedGain, realizedGain per fund | Completed | High | v5.278 | v5.278 | M | fundStats useMemo extended to compute FIFO cost metrics for every fund on every render. | v5.278: computeFIFO() called per fund in fundStats. totalReturn = unrealisedGain + realizedGain. returnPct uses same rpDen logic as FundOverview. returnBasis added to fundStats deps.
F093 | Analysis | FY Summary: Gain vs Net and Gain % columns | Completed | Medium | v5.278 | v5.278 | S | FY Summary table adds two new columns: Gain vs Net Invested at FY-end, and Gain %. | v5.278: hdrs extended with Gain vs Net and Gain %. rows array computes gain_fy and gainPct_fy from running net invested at each financial year end.
F094 | Analysis | XIRR + NPV intentionally unaffected by return basis | Completed | Low | v5.278 | v5.278 | S | XIRR and NPV use actual cash flows — not a cost basis. They are always basis-independent. | Design decision: XIRR = time-weighted efficiency of money deployed. NPV = discounted cash flows. Neither should change with cost basis selection. Only gain% metrics change.
F095 | UX | Return Basis selector in global top header | Completed | High | v5.279 | v5.279 | S | Book / Net / Gross pill always visible on every page in the top nav bar. | v5.279: Compact 3-button pill added to the right-side header row next to the format badge. Clicking instantly re-computes all basis-aware metrics on the current page. Removed duplicate toggle from inside Dashboard hero cards.
F096 | Dashboard | DashboardPage wired: returnBasis in sig + call | Completed | High | v5.279 | v5.279 | S | DashboardPage now correctly receives returnBasis/setReturnBasis as props. | v5.279: Fixed the root cause of v5.277 ReferenceError — DashboardPage sig and call both now include returnBasis and setReturnBasis.
F097 | Analysis | FYSummaryPage: returnBasis wired (Gain % column) | Completed | Medium | v5.279 | v5.279 | S | FY Summary Gain % column uses returnBasis denominator when available. | v5.279: returnBasis passed to FYSummaryPage sig + call. gain_fy uses runningNet. Column headers clarified: 'Gain vs Net Invested' and 'Gain % (vs Net)'.
F098 | Analysis | AnalysisPage: returnBasis wired (fund returnPct) | Completed | Medium | v5.279 | v5.279 | S | Analysis fund cards now show return% using selected basis. | v5.279: returnBasis passed to AnalysisPage sig + call. Fund cards show r.returnPct with basis label: '(book cost)', '(net dep)', or '(gross)'. ¦ v5.285: prop indentation fixed in JSX call.
F099 | Dashboard | Portfolio Timeline: basis-aware cost line | Completed | High | v5.280 | v5.280 | M | Chart dashed baseline changes dynamically with Return Basis selector. | v5.280: Three data series computed per tick: grossData (total invested), netData (invested−redeemed), costData (FIFO book cost of held units). Series label also updates: 'Book Cost (FIFO)' / 'Net Deployed' / 'Gross Invested'. returnBasis added to useMemo deps so chart re-renders on toggle.
F100 | Analysis | FundPerformancePage: Abs Return% column | Completed | Medium | v5.280 | v5.280 | M | Abs Return % column added to Fund Performance comparison table. Respects Return Basis. | v5.280: computeFIFO + computeInvested called per fund in rows useMemo. fpDenom = costBasis / net / grossInvested per returnBasis. Column header shows active basis. returnBasis in rows deps. ¦ v5.285: prop indentation fixed in JSX call.
F101 | Analysis | Multi-portfolio compare page | Completed | High | v5.282 | v5.282 | L | Side-by-side portfolio comparison — ⚖ Compare tab in nav, cards + table, return basis aware. | v5.282: PortfolioComparePage. Tab shows only when 2+ portfolios. Loads each portfolio from _store. 10-row comparison table + summary cards with top 3 holdings.
F102 | Bug Fix | Compare page: COLORS is not defined — crash fix | Completed | Critical | v5.283 | v5.283 | S | Compare page crashed with ReferenceError: COLORS is not defined. | ROOT CAUSE: PortfolioComparePage used 'const C=COLORS' but the app-level color palette is the global const C (defined at module top). COLORS doesn't exist. Fix: replaced with comment — C is already in scope as a module-level constant.
F103 | Perf | Portfolio Timeline chart: pre-filter txns per scheme | Completed | High | v5.283 | v5.283 | S | computeFIFO was called 180 ticks × N schemes per chart render — O(180 × N × T). | v5.283: txnsByScheme={} map pre-built once before the tick loop. computeFIFO now receives pre-filtered array instead of full sortedTxns. Reduces filtering work from 180×N×T to N×T + 180×N — ~180x fewer array scans.
F104 | UX | Fund Overview: sort + filter toolbar now visible | Completed | Medium | v5.283 | v5.283 | S | DataTable sort/filter was already implemented but toolbar only shows when title prop provided. | v5.283: DataTable in FundOverview now receives title prop — e.g. 'Returns & Value — 39 funds'. Toolbar with Filters toggle and CSV download now visible. Click any column header to sort. Filter row appears on toggle.
F105 | Analysis | Funds to Add: refreshed Apr 2025 with Sortino + entry context | Completed | High | v5.283 | v5.283 | M | Recommendations updated with Apr 2025 data — Sortino-ranked, entry-point context, AMFI codes. | v5.283: 5 updated recommendations: Navi Nifty 50 (0.06% TER, Sortino 1.4), Parag Parikh (Sortino 1.6, down 12% from high), Motilal Midcap (32% 3Y XIRR, Sortino 1.8, down 22%), Nippon Small Cap (Sortino 1.3), HDFC Short Duration (rate cut cycle play). Each shows AMFI code + mfapi.in link for direct import.
F106 | Bug Fix | FY+XIRR tables: no render props / no hook-in-arg (blank screen fix) | Completed | Critical | v5.284 | v5.284 | S | Previous attempts caused blank screen (useMemo in fn arg) and raw code dump (arrow fn render props in JSX). | v5.284: All new DataTable columns use pre-formatted string values — no render props needed. XIRR table data computed inline with plain new Date() — no extra hooks. FY col defs placed inside JSX attributes using function() syntax, no arrow fns with JSX returns.
F107 | UX | FY Summary: DataTable sort/filter on main table and fund drill-down | Completed | Medium | v5.284 | v5.284 | M | FY Summary now uses DataTable for both the yearly table and the per-fund drill-down. | v5.284: Main table columns: FY, Invested, Redeemed, Dividends, Net Flow, Portfolio at FY End, Gain vs Net, Gain %. Fund drill-down: Fund, Invested, Redeemed, Net, Txns. Sort by any column, filter by text.
F108 | UX | XIRR Review: per-fund All-Time + Period XIRR sortable table | Completed | Medium | v5.284 | v5.284 | M | New sortable per-fund table below XIRR chart with All-Time and Period XIRR. | v5.284: Computed inline per row — no new hooks. Shows fund name, current value, All-Time XIRR, Period XIRR. Sort by XIRR descending to find best/worst performers. Filter by fund name.
F109 | Fix | Full code audit: 83/84 features verified in code (v5.285) | Completed | High | v5.285 | v5.285 | S | Systematic code audit confirmed 83 of 84 checked features present. One false-positive (INR( in changelog string). | v5.285 audit findings: (1) FundOverviewPage missing returnBasis in JSX call — fixed. (2) FundPerformancePage + AnalysisPage had wrong prop indentation — fixed. (3) FO DataTable title was missing — restored. (4) DataTable confirmed to have full sort (sortKey state, clickable headers) and filter. (5) returnBasis now correctly wired to all 6 key pages: Dashboard, FO, FP, FY, Analysis, Settings.
F110 | Sync | Google Drive sync — sign in, choose folder, save/load data | Completed | High | v5.286 | v5.286 | L | Sign in with Google (OAuth2/GIS), pick Drive folder, save/load portfolio JSON per user. | v5.286: GoogleDrivePanel, gdriveUpload/gdriveDownload, token in _store, setup guide.
F111 | Auth | Email-based login screen at startup | Completed | High | v5.287 | v5.287 | M | Email login at startup — no OAuth, no server. Email is portfolio key. Returning users see recent portfolios. | v5.287: EmailLoginScreen component. Auto-skip if active session exists. Creates new portfolio on first use. Replaces Google OAuth which gave Error 400.
F112 | Auth | Google sign-in (OPTIONAL, key-free fallback) | Completed | High | v5.294 | v6.0 | L | Google is now an OPTIONAL secondary button. The app is 100% functional via open email login with no API keys. | v6.0: demoted to optional. Email login is the primary, fully open-source path. No Google Cloud project required to use the app.
F113 | Auth | Fix: login screen bypassed (useEffect timing bug) | Completed | Critical | v5.295 | v5.295 | M | Restore useEffect fired before currentUserId was set, jumping to setup and bypassing login. | v5.295: onLogin checks _store directly for saved state. Guard added to useEffect.
F114 | Sync | Google Drive save/load from Settings | Completed | High | v5.289 | v5.289 | L | ☁ Save to Drive / ⬇ Load from Drive in Settings → Data Management. Per-portfolio JSON file. | v5.289: gdriveUpload, gdriveDownload, gdriveListFolders, gdriveCreateFolder. Root folder + New folder option.
F115 | UX | Help↔Settings cross-links and anchor navigation | Completed | Medium | v5.288 | v6.1 | S | Clicking a term in Help jumps to the relevant Settings section and vice versa. | v6.1: Help page has a “Jump to settings” bar; goto() switches page, scrolls to the section and highlights it. Anchors: Data Management, Auto-backup, Cloud Sync, Currency.
F116 | Analysis | SIP/SWP calculator — simulate future corpus | Completed | High | v5.289 | v6.1 | M | Enter monthly SIP amount, duration, expected return. Show projected corpus, wealth gained, breakeven. | v6.1: Planning ▸ SIP — monthly amount, period, return, optional annual step-up. Shows projected corpus, invested, wealth gained + growth bars. Pure client-side.
F117 | Analysis | Goal-based tracker — target corpus with timeline | Completed | High | v5.289 | v6.1 | M | Set a financial goal (e.g. ₹2 Cr in 10 years). App shows required monthly SIP and current trajectory. | v6.1: Planning ▸ Goal — target corpus + years + return + step-up + current corpus head-start. Solves required monthly SIP (binary search) and projects existing corpus.
F118 | Tax | FY tax summary — STCG/LTCG breakdown per fund | Completed | High | v5.289 | v6.1 | L | Compute short-term and long-term capital gains per fund per FY. Show tax liability at 15%/10% rates. | v6.1: Tax page — FIFO realised lots classified by holding period (equity >12m LTCG, debt >36m) and grouped per FY. Editable rates; ₹1.25L equity LTCG exemption; strong disclaimer.
F119 | AI | Claude API: auto portfolio commentary and insights | Completed | Medium | v5.290 | v6.1 | L | Send portfolio summary to Claude API. Get plain-English commentary: risks, concentration, suggestions. | v6.1: Insights ▸ Commentary — local rule-based plain-English insights (value, gain, best/worst XIRR, concentration, single-AMC risk, underperformers). Optional AI “Enhance”.
F120 | AI | Anomaly detection — flag unusual transactions | Completed | Low | v5.290 | v6.1 | M | Detect: duplicate transactions, NAV mismatch > 5%, large unexpected redemptions. | v6.1: Insights ▸ Anomaly Scan — 100% local rules: duplicate transactions, NAV/price mismatch >5%, missing price. No data leaves the device.
F121 | AI | Natural language queries — ask about your portfolio | Completed | Low | v5.290 | v6.1 | L | Type 'Which fund has the best XIRR over 3 years?' and get an instant answer from Claude. | v6.1: Insights ▸ Ask — local query parser (best/worst XIRR, largest holding, totals, gain, count) answers instantly; optional AI for free-form.
F122 | Analysis | Sector/industry allocation chart | Completed | Medium | v5.291 | v6.1 | M | Show portfolio breakdown by sector (IT, Finance, Pharma) based on AMFI category data. | v6.1: Analysis ▸ Allocation — by asset class and by derived fund category. Honest note: true stock-sector weights need factsheet holdings, not in the open NAV API.
F123 | Analysis | Fund overlap detection | Completed | Medium | v5.291 | v6.1 | M | Flag funds with similar top holdings. Warn if > 40% portfolio is in overlapping funds. | v6.1: Analysis ▸ Concentration — fund overlap heuristic by shared category cluster; flags >40% in one category. Disclosed as a heuristic.
F124 | Analysis | AMC concentration risk | Completed | Low | v5.291 | v6.1 | S | Show % of portfolio managed by each AMC. Flag if single AMC > 50%. | v6.1: Analysis ▸ Concentration — AMC % with >50% flag, largest single-fund %, and Herfindahl (HHI) diversification score.
F125 | Reporting | PDF report export | Completed | High | v5.292 | v6.1 | L | Export full portfolio report as a PDF: hero metrics, charts, FY table, fund list. | v6.1: Reports page surfaces the existing print/PDF export (hero metrics, holdings, FY, benchmarks, analytics, transactions) — “Save as PDF” in the print dialog.
F126 | Reporting | Monthly email/WhatsApp digest | Completed | Medium | v5.292 | v6.1 | M | Generate a pre-filled mailto: or WhatsApp link with monthly portfolio summary. | v6.1: Reports ▸ Quick digest — pre-filled WhatsApp (wa.me) and mailto links + copy, with a one-glance portfolio summary.
F127 | Sync | Scheduled auto-save to local file | Completed | Medium | v5.292 | v6.1 | M | Auto-save JSON backup to user-chosen folder every N minutes using File System Access API. | v6.1: Settings ▸ Scheduled folder backup — auto-writes timestamped JSON to the chosen folder every 5/15/30/60 min via File System Access API. Pair with Drive/Dropbox sync.
F128 | Mobile | PWA offline mode | Completed | Medium | v5.293 | v6.1 | L | Service worker caches app shell. Works offline after first load. | v6.1: Best-effort offline service worker (cache-first app shell + CDN deps) in a secure context; graceful no-op on file://. Host a sw.js for guaranteed offline.
F129 | Mobile | Touch-optimised chart interactions | Completed | Low | v5.293 | v6.1 | M | Pinch-to-zoom on timeline chart. Swipe to change period on mobile. | v6.1: Timeline chart — two-finger pinch-to-zoom and single-finger tooltip/scrub on touch devices.
F130 | Bug Fix | CRITICAL: data never persisted (_store TDZ bug) | Completed | Critical | v6.0 | v6.0 | S | localStorage was never used — the _store IIFE referenced itself before initialization (temporal dead zone), always threw, and silently fell back to an in-memory map wiped on every reload. | v6.0 ROOT CAUSE of "login does not store/retrieve data". Author wrote _store.set instead of localStorage.setItem inside the feature-test. Rewritten to use localStorage with a true in-memory fallback. This is why re-login never restored anything.
F131 | Persistence | IndexedDB durability mirror + instant save-on-change | Completed | Critical | v6.0 | v6.0 | M | Every state change is debounce-saved (~800ms) to localStorage AND mirrored to IndexedDB. Load falls back to IndexedDB if localStorage is empty/blocked. pagehide + visibilitychange flush on mobile. | v6.0: replaces the unreliable beforeunload+120s-only save. Data now survives refresh, tab close, browser restart and re-login on the same device.
F132 | Auth | Open-source email-first login (no API keys) | Completed | High | v6.0 | v6.0 | M | Email identity is the primary login path and needs no external service, no Google Cloud project, no API key, no subscription. Google remains an optional convenience button. | v6.0: satisfies the fully-open-source requirement. App works offline with zero keys.
F133 | Admin | In-app Feature DB viewer + version number | Completed | High | v6.0 | v6.0 | L | Admin-only Console tab renders the full Feature Registry, Bug Tracker, Change Log, Roadmap and a Status Summary, with the live app version number. Searchable & filterable. | v6.0: the embedded FEATURE_DB is the single source of truth, always current with each release.
F134 | Admin | Feature flags + manage all settings | Completed | High | v6.0 | v6.0 | M | Admin can toggle optional modules (Overview/Performance/FY/XIRR/Analysis/NPV/Compare) on/off via feature flags, and reach every global setting from the console. | v6.0: flags persisted in _store. Non-admins see only enabled tabs.
F135 | Admin | Export Feature DB (CSV) | Completed | Medium | v6.0 | v6.0 | S | One-click export of the registry / bugs / changelog / roadmap to CSV from the Admin console. | v6.0: keeps the external spreadsheet in sync with the in-app DB.
F136 | Open-Source | Open data sources only; no keys or subscriptions | Completed | High | v6.0 | v6.0 | S | NAV/scheme data from MFAPI.in and AMFI (both free & open). Added a free UTI Nifty 50 Index (MFAPI) benchmark so an index line works with no Yahoo dependency. | v6.0: documented in Admin console. No component requires an API key or paid plan.
F137 | Bug Fix | PWA iOS install-tip SyntaxError fixed | Completed | Low | v6.0 | v6.0 | S | Nested single quotes in the iOS tip innerHTML (this.closest('div')) broke the trailing <script>, raising 'Unexpected identifier div'. | v6.0: quotes escaped. PWA install button now wires up correctly.
F138 | Sync | Optional self-hosted cloud sync (PocketBase/CouchDB/REST) | Completed | Medium | v6.1 | v6.1 | M | Push/pull the portfolio state to an open-source backend you run yourself. Free, no subscription; the app is fully usable without it. | v6.1 (roadmap v6.5 delivered). Settings ▸ Cloud Sync. Pushes the same state blob used for local persistence; pull restores & reloads. Needs server CORS for this origin.
F139 | AI | Optional AI provider (built-in or bring-your-own endpoint) | Completed | Low | v6.1 | v6.1 | M | Off by default. Use a built-in assistant (where available) or your own OpenAI-compatible endpoint (e.g. local Ollama — no key). Powers free-form commentary & Q&A only. | v6.1 (roadmap v6.6 delivered). All core insights work with AI off; nothing requires a key or subscription.
F140 | Data Import | Robust flat-RTA statement parser (CAMS + KFintech) | Completed | Critical | v6.2 | v6.2 | M | Unified parser for RTA transaction dumps: normalises underscore/space headers, recognises "Transaction Description" as the type column, parses DD-Mon-YYYY dates, classifies buy/sell/switch/IDCW/SIP, and skips non-transaction admin rows. | v6.2: fixes "Header row not found" (CAMS underscore headers) and "Required columns missing" (KFintech description column). Verified on real statements: CAMS 623 txns / KFintech 201 txns.
F141 | Auth | Google Drive auto-restore on sign-in | Completed | High | v6.2 | v6.2 | M | After Google sign-in, if this device has no local copy, the portfolio is pulled automatically from the user’s Drive (mfa-<id>.json, drive.file scope) and applied. | v6.2: closes the "auto import after logging in" gap. Best-effort and safe — falls back to the upload screen on any failure. Google sign-in moved to the top of the login page.
F142 | Data Import | Import success summary + largest-sheet pick | Completed | Low | v6.2 | v6.2 | S | Upload shows transactions imported, scheme count and skipped non-transaction rows; multi-sheet workbooks auto-select the sheet with the most rows. | v6.2.
F143 | Data Import | Per-folio running balance for RTA imports | Completed | Critical | v6.3 | v6.3 | S | Flat RTA dumps (CAMS/KFintech) carry no balance column. The parser now computes a per-(scheme+folio) cumulative balance via signed unit movements in date order. | v6.3: fixes balance units = 0 and portfolio value = 0 after import. Verified: 31 non-zero holdings on the real CAMS file.
F144 | UI/UX | Pinned React/Babel/XLSX dependencies | Completed | Critical | v6.3 | v6.3 | S | CDN libraries are pinned (react 18.3.1, @babel/standalone 7.29.0, xlsx 0.18.5) to stop version drift breaking JSX compilation. | v6.3: a newer unpinned Babel rejected ">" in JSX text, blanking the app. Pinning restores deterministic builds.
F145 | Analysis | Per-visual export: Excel / SVG / PNG / JPG | Completed | High | v6.3 | v6.3 | M | Every chart exports SVG/PNG/JPG and its underlying data to .xlsx; every data table exports CSV and .xlsx. | v6.3: shared downloadXLSX/downloadChartJPG helpers + ExportBar. Wired into timeline, XIRR, FY, allocation, concentration, tax, holdings, transactions.
F146 | Analysis | Consolidated multi-portfolio totals | Completed | High | v6.3 | v6.3 | M | Compare page shows a combined total across all saved portfolios (value, invested, gain, blended value-weighted XIRR, funds, transactions) with Excel export. | v6.3.
F147 | Analysis | Per-scheme cross-portfolio comparison matrix | Completed | High | v6.3 | v6.3 | M | A scheme×portfolio matrix shows current value of each fund in every portfolio plus combined totals; funds held in >1 portfolio are flagged. Excel export included. | v6.3: directly answers "compare across all portfolios per mutual scheme".
F148 | Scheme Mapping | Persistent mapping overrides (ISIN + name) | Completed | High | v6.3 | v6.3 | M | A manual scheme→AMFI fix is remembered (keyed by ISIN and normalised name) and auto-applied to future imports across portfolios. ISIN-first matching takes priority over fuzzy name matching. | v6.3: stored in mfa_map_overrides; consulted at the top of autoMapScheme.
F149 | Auth | Privacy: recent portfolios hidden by default | Completed | Medium | v6.3 | v6.3 | S | The saved-portfolios list on the login screen is collapsed behind an opt-in "Show saved portfolios" toggle. | v6.3: addresses "recent portfolio should not be shown".
F150 | Scheme Mapping | Abbreviation & plan/option intelligence | Completed | Critical | v6.4 | v6.4 | M | Expands RTA shorthands — Dir-G→Direct Growth, Reg-G→Regular Growth, ABSL→Aditya Birla Sun Life, IDFC→Bandhan etc. Detects plan (Direct/Regular, default Regular) and option (Growth/IDCW). AMC-gated scoring rejects wrong fund houses. | v6.4: 60+ AMC aliases; parseScheme()/matchScore() rewrite. Verified on ABSL/Reg-G/"Growth Growth"/Dir-IDCW examples.
F151 | Scheme Mapping | Purchase-day NAV cross-check disambiguation | Completed | Critical | v6.4 | v6.4 | M | When candidates are close, compares each candidate scheme’s NAV on the transaction date to the recorded price and picks the match within 3%. Confidence + match-method badges shown per row. | v6.4: verifyByNav(); NAV history cached. Badges: ISIN / NAV✓ / saved / high-medium-low.
F152 | Analysis | Global consolidation scope (This / All combined) | Completed | High | v6.4 | v6.4 | L | A header toggle merges every saved portfolio’s transactions + NAV into ALL visuals (Dashboard, Performance, Tax, Analysis, Insights, etc.), deduped. Editing still targets the active portfolio. | v6.4: consolidated memo + effTxns/effNav threaded to visual pages; banner shown in combined mode.
F153 | Data Import | Post-import validation report | Completed | Medium | v6.4 | v6.4 | S | After parsing: transaction & scheme counts, date range, invested/redeemed totals, per-type breakdown, admin rows skipped, and a missing-price warning. | v6.4.
F154 | Data Import | Broker statement header aliases + stronger dedup | Completed | Medium | v6.4 | v6.4 | S | Recognises Groww/Kuvera/MFU/Zerodha column names (order date, order type, traded value, no. of units, etc.). Re-import dedup now keys on ISIN/scheme+folio+date+amount+units. | v6.4.
F155 | Scheme Mapping | Local AMFI master cache | Completed | Low | v6.4 | v6.4 | S | AMFI master list cached locally for 24h — faster mapping and works offline once warmed; stale cache used if network fails. | v6.4.
F156 | Tax | Equity LTCG grandfathering (31-Jan-2018) | Completed | Low | v6.4 | v6.4 | M | For equity units bought on/before 31 Jan 2018, cost basis = max(actual, min(FMV-31Jan2018, sale)) using available NAV. Disclaimer updated. | v6.4.
F157 | Auth | Unified configurable Google Client ID | Completed | Medium | v6.4 | v6.4 | S | Login Google sign-in now uses the same user-set Client ID as Settings, so self-hosters can enable Google on their own domain with no code change. | v6.4.
F158 | Analysis | Equity market-cap allocation (large/mid/small) | Completed | High | v6.5 | v6.5 | M | Break down the equity portion of the portfolio into large/mid/small-cap using per-category models. | v6.5: Market Analysis page. Modeled from fund category (free API gives NAV only, not holdings). Hybrid counted ~70% equity.
F159 | Analysis | Equity sector allocation (modeled) | Completed | High | v6.5 | v6.5 | M | Estimate sector weights (Financials, IT, Pharma, …) across equity holdings; sectoral/thematic funds tilt to their theme. | v6.5: representative Nifty-500-style weights; clearly labeled modeled, not factsheet holdings.
F160 | Analysis | Risk-profile inputs & reallocation recommendations | Completed | High | v6.5 | v6.5 | L | User sets investor profile (Conservative→Very Aggressive or custom sliders); app recommends add/trim per asset class & cap bucket to hit target. | v6.5: presets + custom sliders (asset mix + within-equity cap split), persisted per user. Add/trim amounts vs current.
F161 | UX | Market Analysis separated from Admin/Data-Management settings | Completed | Medium | v6.5 | v6.5 | S | Market analysis / risk profile is its own top-nav page; Settings remains admin & data management only. | v6.5: new "Market Analysis" nav item + feature flag; Settings unchanged (data/admin).
F162 | Sync | Automatic Google Drive backup | Completed | High | v6.6 | v6.6 | M | Once signed in to Google Drive and a folder is chosen, back up automatically on an interval (5/15/30/60 min) with no manual click, plus a first backup shortly after connecting. | v6.6: Settings ▸ Google Drive Sync — "Automatic backup to Drive" toggle + interval; shows last backup time. Silent failures do not spam the UI.
F163 | Sync | Conflict resolution for multi-device Google Drive sync | Completed | High | v6.7 | v6.7 | L | Detects when Drive's copy and the local copy have diverged since the last successful sync (content fingerprint, not clock-based) and lets the user choose Merge / Keep this device / Keep Drive instead of silently overwriting either side. | v6.7: Save/Load and silent auto-backup all run the conflict check first. Merge unions transactions by id (nothing dropped) + merges scheme mappings/NAV cache; settings favor the resolving device. Auto-backup pauses with a visible banner instead of clobbering a newer remote copy.

## 📊 Status Summary
MF ADVISOR — STATUS SUMMARY
v6.9 · Generated 2026-07-21
OVERALL
Status | Count | % of Total
Completed | 163 | 1
Pending | 0 | 0
Other | 0 | 0
TOTAL | 163 | 100%
BY CATEGORY
Category | Total | Done | Pending | % Done
Admin | 3 | 3 | 0 | 1
AI | 4 | 4 | 0 | 1
Analysis | 33 | 33 | 0 | 1
Auth | 7 | 7 | 0 | 1
Bug Fix | 7 | 7 | 0 | 1
Dashboard | 11 | 11 | 0 | 1
Data Import | 16 | 16 | 0 | 1
Display Format | 9 | 9 | 0 | 1
Fix | 1 | 1 | 0 | 1
Help & Docs | 6 | 6 | 0 | 1
Mobile | 2 | 2 | 0 | 1
Multi-Currency | 3 | 3 | 0 | 1
NAV | 9 | 9 | 0 | 1
Open-Source | 1 | 1 | 0 | 1
Perf | 1 | 1 | 0 | 1
Persistence | 1 | 1 | 0 | 1
Reporting | 2 | 2 | 0 | 1
Scheme Mapping | 14 | 14 | 0 | 1
Settings | 7 | 7 | 0 | 1
Sync | 6 | 6 | 0 | 1
Tax | 2 | 2 | 0 | 1
UI/UX | 1 | 1 | 0 | 1
UX | 17 | 17 | 0 | 1

## 🧩 Gap Analysis
MF ADVISOR — GAP ANALYSIS & SOLUTIONS
v6.9 · from user feedback · 27 gaps
ID | Area | Gap / Issue | Severity | Status | Solution Approach
G01 | Regression/Crash | React #300 crash / blank visuals after import | Critical | Fixed v6.3 | Move all hooks above early returns; pin Babel.
G02 | Regression/Data | Balance units = 0 for all imported transactions | Critical | Fixed v6.3 | Compute per-folio running balance in the parser.
G03 | Regression/Data | Portfolio value always 0 | Critical | Fixed v6.3 | Resolved via G02.
G04 | Scheme Mapping | Mapping logic poor; wrong/again-and-again matching | High | Done v6.4 | ISIN-first match + persistent overrides + 24h local AMFI master cache.
G05 | Scheme Mapping | Direct/Regular & Growth/IDCW mismatched | High | Done v6.4 | Abbreviation/AMC expansion, plan/option detection (Regular default), AMC-gated scoring, purchase-day NAV cross-check.
G06 | Scheme Mapping | Manual override not persistent | Medium | Fixed v6.3 | mfa_map_overrides keyed by ISIN/name, auto-applied.
G07 | Multi-Portfolio | Cannot combine multiple portfolios | High | Done v6.3 | Consolidated totals across all saved portfolios on Compare.
G08 | Multi-Portfolio | Visuals/reports do not reflect combined portfolios | High | Done v6.4 | Global This/All-combined scope merges every portfolio into all visuals (deduped).
G09 | Multi-Portfolio | No compare across portfolios per scheme | High | Done v6.3 | Per-scheme cross-portfolio matrix with Excel export.
G10 | Privacy/Login | Recent portfolios shown on login | Medium | Fixed v6.3 | Hidden behind opt-in reveal.
G11 | Visual Export | No per-visual Excel export | High | Done v6.3 | downloadXLSX on every chart & table.
G12 | Visual Export | No per-visual SVG/PNG/JPG export | High | Done v6.3 | SVG serialize + canvas PNG/JPG on every chart.
G13 | Auth | Google sign-in only works on one domain | Medium | Done v6.4 | Google Client ID configurable in Settings and used by login.
G14 | Auth/Sync | Drive auto-restore needs prior save + scope | Medium | Partial v6.4.2 — auto-restore on sign-in works; auto-save to Drive still planned | Drive auto-restore on sign-in shipped; manual push in Settings. Auto-save on first import planned.
G15 | Import | No broker exports (Zerodha/Groww/MFU) | Medium | Done v6.4 | Broker header aliases (Groww/Kuvera/MFU/Zerodha) over the flat-RTA core.
G16 | Import | Password-protected CAS PDFs unsupported | Low | Open v6.5 | Client-side PDF decryption with user password.
G17 | Import | Re-import can duplicate transactions | Medium | Done v6.4 | Re-import dedup keys on ISIN/scheme+folio+date+amount+units.
G18 | Data Quality | NAV gaps for merged/closed schemes | Medium | Open v6.5 | Manual NAV CSV per scheme + flagged interpolation.
G19 | UX/Trust | No clear post-import validation summary | Medium | Done v6.4 | Structured post-import validation report (counts, types, range, totals, warnings).
G20 | Tax | FIFO vs broker method / changing rules | Low | Done v6.4 | Equity LTCG grandfathering (31-Jan-2018 FMV floor) where NAV available.
G21 | QA/Validation | Undefined-function bugs (e.g. gdriveCreateFolder) shipped because visual checks do not exercise every button handler | High | Done v6.4 | Static audit: strip comments/strings, list all definitions, flag bare calls with no matching definition. Run before every release.
G22 | Data Integrity | New transactions silently excluded when their fund is disabled or flagged exited | High | Done v6.4.1 | Auto-enable the fund on add/edit + force Show-Exited; verified the engine then counts units & invested.
G23 | Data Quality | Risk analytics N/A due to thin NAV history not being backfilled | High | Done v6.4.2 | NAV refresh re-downloads full history for funds with <30 points; analytics then compute.
G24 | UX Defaults | Default fund selection too small; exited funds shown by default | Medium | Done v6.4.2 | Default all funds enabled (no NAV filter), exited deselected by default.
G25 | Data Source | True stock-level & exact sector allocation need factsheet holdings, absent from the free AMFI/MFAPI NAV feed | Medium | Mitigated v6.5 | Model market-cap & sector from fund category with clear "modeled, not factsheet" disclosure; upgrade to a real holdings dataset when available (roadmap).
G26 | Data Integrity | A second, separate code path (JSON/backup import) had the same NAV-gated enabled-set bug already fixed elsewhere | High | Done v6.8 | Applied the same enable-all-imported-schemes fix to onImportFromJSON.
G27 | Scheme Mapping | Category-name/option-token collisions ("Dividend Yield" containing "dividend") can misdetect the option variant | High | Done v6.9 (Dividend Yield); audited CAT_WORDS/plan-opt token lists for further collisions — none found in real Indian MF category names | Strip known category phrases before option-token detection. Audit method: built parseScheme/matchScore/detectOption/detectAMC from source and ran them offline against 86 real scheme names extracted from an actual transaction export, checking AMC detection coverage, plan/option correctness, and AMC-gate rejection of wrong-house candidates.

## 🐛 Bug Tracker
MF ADVISOR — BUG & ISSUE TRACKER
Known issues · root causes · fixes applied
Bug ID | Feature ID | Category | Title | Status | Severity | Root Cause | Fix Applied | Ver Fixed | Reported
B001 | F022-F038 | Multi-Currency | INR() hardcoded in 55+ JSX call sites — currency switch had no effect | Fixed | Critical | FMT() existed but only 17 of 72 call sites used it. Dashboard hero cards, FY Summary, XIRR Review, NPV all used INR(). | v5.273: Replaced all INR() with FMT() via regex pass. Verified 0 INR() calls remain. | v5.273 | 2024-03-22
B002 | F041 | Analysis | Show/hide exited: filteredEnabledSet missing — exited funds still in calculations | Fixed | High | showExited filtered sidebar list only. enabledSet (unfiltered) was passed to all 7 page components. Exited funds affected all calculations. | v5.273: filteredEnabledSet useMemo added in App. When showExited=false, filters out exited fund names. Passed to all 7 pages. | v5.273 | 2024-03-22
B003 | F002 | Data Import | Folio separator rows included in transaction list (multi-folio CAS) | Fixed | High | rawBalCheck/rawMVCheck guard was in v5.262 parseXLS() but dropped in revert to v5.113 base. | v5.273: Re-added 2-line folio separator check (rawBalCheck==='--' && rawMVCheck==='--') in parseXLS() row loop. | v5.273 | 2024-03-22
B004 | F008 | Data Import | No way to append new XLS transactions without full re-import | Fixed | High | appendXLS callback was in v5.262 but dropped. Users had to re-import entire file or add transactions one by one. | v5.273: appendXLS useCallback re-added. Deduplicates by date¦scheme¦type¦amount key. Button added in Data Management. | v5.273 | 2024-03-22
B005 | F039 | Settings | No validation of transaction data | Fixed | High | runValidation with 6 rules was in v5.262 rebuild but absent in v5.272. Users had no way to spot duplicates or missing NAV. | v5.273: runValidation (6 rules: future dates, missing amount, no NAV, NAV mismatch >10%, duplicates, missing scheme). Panel with filter/dismiss/re-run in Data Management. | v5.273 | 2024-03-22
B006 | F025 | Dashboard | Dashboard KPI hero cards showed ₹ regardless of currency setting | Fixed | Critical | heroStats.pv, heroStats.gain, heroStats.invested, heroStats.net all rendered via INR() in DashboardPage JSX. | v5.273: All INR() replaced with FMT() globally. Hero cards now respect G_CURRENCY. | v5.273 | 2024-03-22
B007 | F035 | Analysis | FY Summary page monetary values hardcoded in ₹ | Fixed | High | FYSummaryPage had 19 INR() calls for invested, redeemed, dividends, net flow, portfolio value. | v5.273: All 19 INR()→FMT() replaced. | v5.273 | 2024-03-22
B008 | F036 | Analysis | XIRR Review chart tooltips and table used hardcoded ₹ | Fixed | High | XirrReviewPage and XIRRHistoryChart both used INR(). 5 INR() calls in chart tooltip builder strings. | v5.273: All INR()→FMT() replaced. | v5.273 | 2024-03-22
B009 | F038 | Analysis | NPV page values hardcoded in ₹ | Fixed | Medium | NpvPage used INR() for NPV display and chart Y-axis. | v5.273: INR()→FMT() replaced. | v5.273 | 2024-03-22
B010 | F032 | Dashboard | NAV date not shown in Portfolio Value card | Open | Low | navAsOf()/navDaysStale not yet added. Sub-label hardcoded to 'Current market value'. | Planned for v5.274: Add navAsOf() function and navDaysStale useMemo in DashboardPage. | — | 2024-03-22
B011 | F069 | UX | Babel blank screen — literal newline in JS string | Fixed | Critical | join('\n') written with real newline inside single-quoted string. Babel: Unterminated string constant. | v5.272: Changed to join('\\n'). Added automated literal-newline scan before deploy. | v5.272 | 2024-03-21
B012 | F064 | UX | Edge Tracking Prevention blocked localStorage → blank screen | Fixed | Critical | Edge blocks localStorage on file:// protocol. Every _store.get() returned null, app stuck in 'loading' state. | v5.272: _store wrapper tries localStorage, falls back to in-memory Map. | v5.272 | 2024-03-22
B013 | F130 | Persistence | Data never saved or restored across sessions | Fixed | Critical | const _store=(()=>{..._store.set(...)...})() referenced _store during its own initialization (TDZ) so the localStorage test always threw and the in-memory fallback was always used. Nothing was ever written to disk. | v6.0: rewrote _store to call localStorage.setItem/getItem directly with a separate in-memory fallback flag. Added IndexedDB mirror + debounced save-on-change. | v6.0 | 2026-06-02
B014 | F137 | PWA | iOS tip script: Unexpected identifier 'div' | Fixed | Low | this.closest('div') inside a single-quoted innerHTML string terminated the string early. | v6.0: escaped the inner quotes. | v6.0 | 2026-06-02
B015 | F132 | Auth | Google sign-in required a Google Cloud Client ID (API key) | Fixed | High | Primary login path depended on a hardcoded OAuth Client ID tied to one Google project — conflicts with open-source/no-key requirement. | v6.0: email login made primary & fully key-free; Google demoted to optional. | v6.0 | 2026-06-02
B016 | F140 | Data Import | CAMS RTA upload: "Header row not found" | Fixed | Critical | parseXLS searched for the literal substrings "transaction date"/"scheme name" (space-separated). CAMS RTA exports use underscores: SCHEME_NAME, TRADE_DATE, TRANSACTION_TYPE — so no header matched. | v6.2: new parseFlatRTA normalises headers (underscores/dots → spaces) and matches trade date / transaction type with priority ordering. | v6.2 | 2026-06-04
B017 | F140 | Data Import | KFintech upload: "Required columns missing" | Fixed | Critical | The type column in KFintech exports is labelled "Transaction Description", but the parser only accepted "transaction type"/"type", so the Type column was not found. | v6.2: type-column matcher now also accepts "transaction description"/"description"; scheme matcher accepts "scheme description". | v6.2 | 2026-06-04
B018 | F141 | Auth | Portfolio not auto-imported after Google login | Fixed | High | Google sign-in only restored LOCAL data; it never pulled the portfolio saved in the user’s Google Drive, so a fresh device showed an empty upload screen. | v6.2: after sign-in, auto-download mfa-<id>.json from Drive and apply via the JSON-restore path when local is empty. | v6.2 | 2026-06-04
B019 | F144 | UI/UX | App blank after import — React error #300 / Babel rejects ">" in JSX | Fixed | Critical | Two causes: (1) a touch-handler useRef in LineChart sat AFTER an early return, changing hook count on empty charts (React #300); (2) the unpinned @babel/standalone updated and began rejecting raw ">" inside JSX text. | v6.3: moved all hooks above early returns; pinned React 18.3.1 / Babel 7.29.0 / xlsx 0.18.5. | v6.3 | 2026-06-20
B020 | F143 | Data Import | Balance units = 0 and portfolio value = 0 after CAMS/KFintech import | Fixed | Critical | The new flat-RTA parser hardcoded balUnits:0, but the engine treats an import row's balUnits as the authoritative cumulative balance — so holdings and value computed to zero. | v6.3: compute per-(scheme+folio) running balance with unitSign() in date order; clamp float dust to 0. | v6.3 | 2026-06-20
B021 | F148 | Scheme Mapping | Poor scheme mapping; manual fixes not remembered | Fixed | High | Matching relied on fuzzy fund-name search; manual corrections were not persisted, so re-imports reverted to wrong matches. | v6.3: ISIN-first matching + persistent overrides keyed by ISIN and normalised name, auto-applied on future imports. | v6.3 | 2026-06-20
B022 | F150 | Scheme Mapping | Common shorthands (Dir-G, Reg-G, ABSL, "Growth Growth") not recognised | Fixed | High | Matcher used raw token overlap with a tiny AMC lock list; it could not expand RTA abbreviations or default unspecified plans to Regular. | v6.4: parseScheme() expands 60+ AMC aliases + plan/option tokens; matchScore() gates on AMC and scores plan/option. NAV cross-check confirms. | v6.4 | 2026-06-22
B023 | F114 | Sync | Create/manage Google Drive folder did not work | Fixed | High | gdriveCreateFolder() was called by the "+ New" button but was never defined (only referenced in the changelog), and was invoked with token.access_token while sibling helpers expect the token object — so clicking it threw and folder creation/management silently failed. | v6.4: implemented gdriveCreateFolder(token,name,parentId) (reuses an existing same-named folder, drive.file scope), fixed the call site to pass the token object, and surfaced create status. Added a static audit pass (strip comments/strings → flag bare calls with no definition) to catch this class of bug. | v6.4 | 2026-06-23
B024 | F052 | Settings | Manually-added transactions not reflected in Portfolio Value / Invested | Fixed | High | Portfolio Value and Invested only sum ENABLED, non-exited funds (enabledSet / filteredEnabledSet filter). Adding a transaction to a fund that was not enabled — or that showed as "exited" because a prior balance was ~0 — left it excluded, so the new amount/units never appeared. The Add/Edit handler appended the transaction but never enabled its scheme. (Also: my first fix referenced setEnabled/setShowExited which were NOT passed to SettingsPage — would have crashed; props now wired.) | v6.4.1: Add & Edit transaction handlers now add the scheme to the enabled set and force Show-Exited on, so the fund is counted immediately. setEnabled/setShowExited threaded into SettingsPage. Verified: a manual buy on a fully-exited fund restores units and adds to Invested. | v6.4.1 | 2026-06-24
B025 | F037 | Analysis | Cost & risk analytics (Sharpe/Sortino/StdDev) show N/A after revalidation | Fixed | High | computeFundAnalytics needs ≥30 NAV points / ≥12 monthly samples. fetchNavBackground SKIPPED any fund whose last NAV date was current — even if it held only a few points — so thin-history funds never backfilled and every risk metric stayed N/A. | v6.4.2: backfill — if a fund has <30 NAV points, re-download the FULL series even when the latest date is current. Verified analytics then return Sharpe/Sortino/StdDev. | v6.4.2 | 2026-06-26
B026 | F052 | Settings | Only a subset of funds enabled on reload (e.g. 38/86) | Fixed | High | On load the enabled set was filtered by `s=>nb[s]` — funds whose NAV had not yet downloaded were dropped from the selection every reload, shrinking the count and hiding their value. | v6.4.2: enabled set no longer filtered by NAV presence; default = ALL funds, saved selection respected in full. Exited funds deselected by default (showExited=false). | v6.4.2 | 2026-06-26
B027 | F052 | Data Import | Transactions from "Restore backup"/JSON import excluded from Portfolio Value until NAV loads | Fixed | High | onImportFromJSON built the enabled-fund set by filtering to schemes with navByScheme already present (`filter(s=>nb[s])`) — the same class of bug fixed in v6.4.2 for the login-restore path, but this second import path was missed. A JSON import with no/partial navByScheme (e.g. ISIN-only scheme mapping) enabled ZERO funds, so Portfolio Value/Invested showed 0 until NAV finished fetching. | v6.8: onImportFromJSON now enables every scheme found in the imported transactions regardless of NAV load state, matching the fix already applied to the login-restore path. | v6.8 | 2026-07-21
B028 | F150 | Scheme Mapping | "Dividend Yield" fund category misread as IDCW option, mismapping Growth-plan schemes | Fixed | High | Audited the scheme-mapping engine (parseScheme/matchScore) against 86 real scheme names from a live transaction export. detectOption() flags any name containing "dividend" as IDCW unless the literal word "growth" is present — but RTA statements abbreviate Growth as "-G", never spelling it out, so any Growth-plan scheme whose CATEGORY is "Dividend Yield" (a common category run by ABSL, ICICI Pru, UTI, Templeton, Sundaram, Tata) was misclassified as an IDCW option, e.g. "ABSL Dividend Yield Reg-G" → wrongly read as IDCW instead of Growth. This could map a holding to the wrong option-variant scheme code, causing NAV/return errors. | v6.9: detectOption() strips the phrase "dividend yield" before testing for IDCW/payout tokens, so the category name no longer triggers a false IDCW read. Verified against all 3 affected schemes in the real corpus plus 5 control cases (explicit IDCW/Growth schemes unaffected). | v6.9 | 2026-07-21

## 📝 Change Log
MF ADVISOR — CHANGE LOG
History of all changes by version
Version | Date | Type | Feature ID | Change | Author
6.9 | 2026-07-21 | Fix | F150 | Scheme-mapping audit (86 real scheme names) found and fixed a real mismap: "Dividend Yield" fund category (ABSL/ICICI Pru/UTI/Templeton/Sundaram/Tata) was misread as an IDCW option due to the word "dividend", even on Growth-plan schemes named with the RTA "-G" suffix. detectOption() now excludes the category phrase before scanning for option tokens. | Dev
6.8 | 2026-07-21 | Fix | F052 | Fixed a second occurrence of the NAV-gated enabled-set bug in the Restore-backup/JSON-import path — imported transactions now count in Portfolio Value & Invested immediately, without waiting for NAV to load. | Dev
6.7 | 2026-07-21 | Feature | F163 | Google Drive sync now detects multi-device conflicts (fingerprint-based) and offers Merge / Keep this device / Keep Drive, instead of silently overwriting. Auto-backup pauses and flags a conflict banner rather than clobbering newer remote data. | Dev
6.6 | 2026-07-21 | Feature | F162 | Automatic Google Drive backup — toggle + interval (5/15/30/60 min) in Settings ▸ Google Drive Sync; backs up shortly after connecting and thereafter on schedule. | Dev
6.5 | 2026-06-28 | Feature | F158-F160 | New Market Analysis page: equity market-cap & sector breakdown, investor risk-profile inputs (presets + custom sliders), and add/trim reallocation recommendations. Sector/cap weights are modeled from fund category and labeled as such. | Dev
6.5 | 2026-06-28 | Change | F161 | Market Analysis is now a separate top-nav page; Settings remains Admin / Data Management only. | Dev
6.4.2 | 2026-06-26 | Fix | F037 | Risk analytics (Sharpe/Sortino/StdDev/Beta/Alpha) no longer stuck on N/A — NAV refresh now backfills the full history for funds with too few points. | Dev
6.4.2 | 2026-06-26 | Fix | F052 | All funds enabled by default (reload no longer drops funds whose NAV had not loaded); exited funds deselected by default. | Dev
6.4.1 | 2026-06-24 | Fix | F052 | Manually added/edited transactions now immediately reflect in Portfolio Value and Invested — the fund is auto-enabled and surfaced even if previously exited. (Fixed a scope bug where the setters were not passed to Settings.) | Dev
6.4 | 2026-06-23 | Fix | F114 | Fixed Google Drive folder create/manage (gdriveCreateFolder was undefined + wrong arg). Added an undefined-function static audit to the release checklist. | Dev
6.4 | 2026-06-22 | Fix | F150,F151 | MAJOR scheme-mapping overhaul: expands Dir-G/Reg-G/ABSL/IDFC etc., detects plan & option (Regular default), AMC-gated scoring, and purchase-day NAV cross-check to disambiguate. Confidence badges per row. | Dev
6.4 | 2026-06-22 | Feature | F152 | Global consolidation: a This/All-combined toggle merges every saved portfolio into ALL charts, tables and reports (deduped). | Dev
6.4 | 2026-06-22 | Feature | F153,F154 | Post-import validation report; broker header aliases (Groww/Kuvera/MFU/Zerodha); stronger re-import dedup. | Dev
6.4 | 2026-06-22 | Feature | F155,F156,F157 | 24h AMFI master cache; equity LTCG grandfathering (31-Jan-2018); unified configurable Google Client ID for login. | Dev
6.3 | 2026-06-20 | Fix | F143,F144 | CRITICAL: fixed app-blank-after-import (React #300 + Babel drift) and balance-units/portfolio-value = 0 (per-folio running balance). Dependencies pinned. | Dev
6.3 | 2026-06-20 | Feature | F145 | Per-visual export: every chart → SVG/PNG/JPG + Excel; every table → CSV + Excel. | Dev
6.3 | 2026-06-20 | Feature | F146,F147 | Multi-portfolio: consolidated combined totals + per-scheme cross-portfolio comparison matrix, both with Excel export. | Dev
6.3 | 2026-06-20 | Feature | F148 | ISIN-first scheme mapping with persistent manual overrides auto-applied to future imports. | Dev
6.3 | 2026-06-20 | Feature | F149 | Privacy: recent portfolios hidden behind an opt-in reveal on the login screen. | Dev
6.2 | 2026-06-04 | Fix | F140 | CAMS RTA statement import fixed (underscore headers) + KFintech import fixed (Transaction Description column). New robust flat-RTA parser skips admin rows; verified on real files. | Dev
6.2 | 2026-06-04 | Feature | F141 | Google Drive auto-restore after sign-in; Google sign-in moved to the top of the login page. | Dev
6.2 | 2026-06-04 | Feature | F142 | Import success summary (imported/skipped/schemes) + largest-sheet selection for multi-sheet workbooks. | Dev
6.1 | 2026-06-03 | Feature | F116-F117 | Planning page: SIP/SWP calculator (with step-up) and goal-based corpus planner that solves the required monthly SIP. | Dev
6.1 | 2026-06-03 | Feature | F118 | Tax page: FIFO STCG/LTCG per fund per financial year, equity/debt holding-period classification, editable rates and ₹1.25L equity LTCG exemption. | Dev
6.1 | 2026-06-03 | Feature | F122-F124 | Analysis: Allocation (asset class & category) and Concentration (AMC %, single-fund %, HHI, fund-overlap heuristic). | Dev
6.1 | 2026-06-03 | Feature | F119-F121,F139 | Insights: local commentary, anomaly scan and Q&A — fully offline. Optional AI (built-in or self-hosted Ollama/OpenAI-compatible), off by default. | Dev
6.1 | 2026-06-03 | Feature | F125-F126 | Reports page: one-click PDF export and a shareable WhatsApp/Email digest. | Dev
6.1 | 2026-06-03 | Feature | F127 | Settings: scheduled auto-backup to a chosen folder (5/15/30/60 min) via File System Access API. | Dev
6.1 | 2026-06-03 | Feature | F138 | Optional self-hosted cloud sync (PocketBase/CouchDB/custom REST) — push/pull across devices on a server you own. | Dev
6.1 | 2026-06-03 | Feature | F128-F129 | Best-effort offline service worker; pinch-to-zoom & touch scrubbing on the timeline chart. | Dev
6.1 | 2026-06-03 | Feature | F115 | Help ↔ Settings cross-links with scroll-to-section highlight. | Dev
6.0 | 2026-06-02 | Fix | F130 | CRITICAL: fixed _store TDZ bug — the app never actually used localStorage, so data was never saved or restored. Now persists reliably. | Dev
6.0 | 2026-06-02 | Feature | F131 | IndexedDB durability mirror + debounced save-on-change + pagehide/visibilitychange flush. Data survives refresh, close, restart and re-login. | Dev
6.0 | 2026-06-02 | Feature | F132 | Open-source email-first login. No API keys, no Google Cloud project, no subscription required. Google demoted to optional. | Dev
6.0 | 2026-06-02 | Feature | F133-F135 | Admin Console: in-app Feature DB viewer (registry/bugs/changelog/roadmap/summary) with live version number, feature flags, settings management, and CSV export. | Dev
6.0 | 2026-06-02 | Feature | F136 | Open data sources only (MFAPI.in + AMFI). Added free UTI Nifty 50 Index benchmark to remove Yahoo dependency for the index line. | Dev
6.0 | 2026-06-02 | Fix | F137 | Fixed PWA iOS tip SyntaxError (nested quotes in this.closest('div')). | Dev
v5.273 | 2024-03-23 | Fix | F022 | Replaced all 55 INR() calls with FMT() — currency now works on Dashboard, FY Summary, XIRR Review, NPV, Fund Overview | Dev
v5.273 | 2024-03-23 | Fix | F041 | Added filteredEnabledSet in App — show/hide exited funds now filters all page calculations, not just sidebar list | Dev
v5.273 | 2024-03-23 | Fix | F002 | Re-added folio separator fix in parseXLS() — rawBalCheck/rawMVCheck guard skips '--' rows in multi-folio CAS | Dev
v5.273 | 2024-03-23 | Feature | F008 | appendXLS callback added — import more transactions from XLS with deduplication | Dev
v5.273 | 2024-03-23 | Feature | F054 | Append XLS Transactions button added to Data Management card | Dev
v5.273 | 2024-03-23 | Feature | F039 | runValidation added — 6 rules (future dates, missing amounts, no NAV, NAV mismatch, duplicates). Panel with filter/dismiss/re-run in Settings. | Dev
v5.272 | 2024-03-22 | Fix | F013 | AMC_LOCK in matchScore — prevents cross-AMC mismatches (ABSL→Edelweiss, Nippon→Invesco etc) | Dev
v5.272 | 2024-03-22 | Feature | F015 | Inline scheme mapping edit with live MFAPI search dropdown per row | Dev
v5.272 | 2024-03-22 | Fix | F016 | smEditPick clears old navByScheme entry before re-fetch | Dev
v5.272 | 2024-03-22 | Feature | F019 | Refresh All NAV button — re-fetches NAV for all mapped schemes at once | Dev
v5.272 | 2024-03-22 | Feature | F020 | bulkUploadSchemeMapping — CSV upload for scheme/AMFI code mapping in bulk | Dev
v5.272 | 2024-03-22 | Feature | F009 | bulkUploadTransactionsCSV — CSV upload for transactions with deduplication | Dev
v5.272 | 2024-03-22 | Feature | F049 | Dataset status banner at top of SettingsPage | Dev
v5.272 | 2024-03-22 | Fix | F064 | _store wrapper — Edge Tracking Prevention fix, falls back to in-memory storage | Dev
v5.272 | 2024-03-22 | Fix | F065 | Loading screen: 5-second safety timeout + Start Fresh button | Dev
v5.272 | 2024-03-22 | Fix | B011 | join('\n') literal newline in Babel script fixed — was causing silent crash → blank screen | Dev
v5.1 | 2024-01-01 | Feature | F011 | Folder/directory auto-save via File System Access API | Dev
v5.1 | 2024-01-01 | Feature | F060 | Multi-user profiles | Dev
v5.1 | 2024-01-01 | Feature | F062 | Export HTML, Word, Print | Dev
v5.0 | 2023-06-01 | Feature | F001 | Initial release: CAMS import, Dashboard, Fund Overview, Performance, FY Summary, XIRR, Analysis, NPV, Settings, Help | Dev
v5.274 | 2024-03-30 | Fix | F079 | BLANK SCREEN FIX: duplicate function FMT() and let G_CURRENCY= declarations removed. Root cause: new infrastructure added ON TOP of old block. Fix: replace old block in one shot from v5.273 clean base. | Dev
v5.274 | 2024-03-30 | Feature | F070 | applyFMT() engine: currency×rate, auto/manual scale, 0-4 decimals, neg style (−/parens/abs), thousands sep (Indian/Intl/none), zero display. customFmt() for Excel-style strings. | Dev
v5.274 | 2024-03-30 | Feature | F071-F073 | 6 format presets + live preview + fine controls (6 controls in 3-col grid) in Settings → Display Format. | Dev
v5.274 | 2024-03-30 | Feature | F074-F076 | Custom format string input. Editable exchange rates. SGD + GBP added (6 currencies total). | Dev
v5.274 | 2024-03-30 | Feature | F077-F078 | Header format badge replaces currency dropdown. displayFmt persisted in JSON backup. | Dev
v5.274 | 2026-04-01 | Bug | F080 | FIXED: 'displayFmt is not defined' crash in Settings — deployed file was missing displayFmt/applyDisplayFmt in SettingsPage prop signature. Redeployed from correct working file. | Dev
v5.274 | 2026-04-01 | Perf | F081 | Incremental NAV fetch: skip schemes already current, use /latest endpoint for stale schemes with existing data, full fetch only for empty schemes. Eliminates redundant downloads. | Dev
v5.275 | 2026-04-02 | Perf | F082-F084 | Separate NAV cache key (mfa_nav_v1_{user}). Parallel fetch 5 concurrent. /latest endpoint for stale schemes. ~5x faster daily refresh. | Dev
v5.275 | 2026-04-02 | Feature | F085 | RootErrorBoundary: App crashes show error message + Reload button instead of blank screen. | Dev
v5.275 | 2026-04-02 | Feature | F032,F056 | navAsOf(): Portfolio Value sub-label shows 'NAV current' or 'NAV N days old' dynamically. | Dev
v5.275 | 2026-04-02 | Fix | — | Root cause fixed: ReactDOM.class prefix on RootErrorBoundary caused Babel crash in v5.275 first attempt. Now standalone class before createRoot. | Dev
v5.276 | 2026-04-03 | Feature | F003,F005,F006,F007 | Auto-detect import: CAMS XLSX, KFintech XLSX, Generic CSV + .csv file input. parseAnyFile() routes automatically. | Dev
v5.276 | 2026-04-03 | Feature | F021 | Skip (exited) button in Scheme Mapping for zero-balance schemes. Fixed: wrapped in React Fragment to prevent adjacent JSX crash. | Dev
v5.276 | 2026-04-03 | Docs | F045-F048,F066 | Help updated: Getting Started (all formats), Settings rewritten, Display Format + Getting Help sections, Technical Glossary (12 definitions). | Dev
v5.276 | 2026-04-03 | Fix | — | Root cause of blank screen: Skip IIFE placed as 2nd child inside &&() without Fragment. Fixed with <> wrapper. | Dev
v5.277 | 2026-04-08 | Bug | F086 | FIXED: returnBasis not in DashboardPage scope. Root cause: changes applied to wrong file state. Fix: atomic 13-change patch from v5.276 clean base with 29-check verification. | Dev
v5.277 | 2026-04-08 | Feature | F087-F090 | Return basis selector: Book Cost (FIFO) / Net Deployed / Gross Invested. Toggle on Dashboard + Settings. 6 hero cards. heroStats computes all 3 gain bases every render. | Dev
v5.278 | 2026-04-12 | Feature | F091-F093 | Return basis propagated to FundOverview (Abs Return % denominator + dynamic label), fundStats (costBasis, returnPct, unrealisedGain, realizedGain per fund), FY Summary (Gain vs Net + Gain % columns). | Dev
v5.278 | 2026-04-12 | Docs | F094 | XIRR and NPV confirmed intentionally basis-independent. They use actual cash flows — not a cost basis measure. | Dev
v5.279 | 2026-04-17 | Feature | F095-F098 | Return Basis selector in global top header (Book/Net/Gross pill). Visible on every page. FYSummaryPage + AnalysisPage wired. DashboardPage prop bug fixed. | Dev
v5.280 | 2026-04-17 | Feature | F099-F100 | Portfolio Timeline chart: dashed baseline changes with basis selection (Book Cost / Net Deployed / Gross Invested). Fund Performance page: Abs Return % column added, basis-aware denominator. | Dev
v5.281 | 2026-04-17 | Feature | F004 | CAMS Current Value XLSX: parseCAMSCurrentValue() auto-detected via cams_cv format code. Seeds current holdings snapshot. | Dev
v5.281 | 2026-04-17 | Feature | F067 | Multi-portfolio system: Users → Portfolios rename throughout UI — header, modal title, add/delete/switch copy, placeholder text. | Dev
v5.282 | 2026-04-18 | Feature | F042/F101 | Multi-portfolio Compare page: ⚖ Compare tab auto-appears for 2+ portfolios. Side-by-side cards + comparison table. Loads inactive portfolios from _store. Return basis aware. | Dev
v5.283 | 2026-04-19 | Bug | F102 | FIXED: Compare page crash — COLORS not defined. Was using undefined 'COLORS' instead of module-level 'C'. | Dev
v5.283 | 2026-04-19 | Perf | F103 | Chart perf: txns pre-filtered per scheme before FIFO loop. ~180x fewer array scans per chart render. | Dev
v5.283 | 2026-04-19 | Feature | F104 | Fund Overview DataTable sort/filter toolbar now visible via title prop. | Dev
v5.283 | 2026-04-19 | Feature | F105 | Funds to Add refreshed Apr 2025: Sortino-ranked, entry-point context, AMFI codes shown for direct import. | Dev
v5.284 | 2026-04-24 | Bug | F106 | FIXED blank screen: no useMemo-in-arg, no arrow fn render props. Pre-formatted string values in DataTable columns. | Dev
v5.284 | 2026-04-24 | Feature | F107,F108 | FY Summary DataTable (sort/filter on yearly + fund tables). XIRR per-fund table (All-Time + Period XIRR sortable). | Dev
v5.285 | 2026-04-26 | Fix | F109 | Code audit: 83/84 features verified. Fixed: FundOverviewPage returnBasis missing from JSX call. Fixed: FP+Analysis prop indentation. Restored: FO DataTable title. Confirmed: DataTable has sort+filter. | Dev
v5.286 | 2026-04-29 | Feature | F110 | Google Drive Sync: sign in with Google OAuth2, choose Drive folder, save/load portfolio JSON per user. Setup guide for Google Cloud Client ID included. | Dev
v5.286 | 2026-04-29 | Fix | F109 | returnBasis now correctly wired to FundOverview, FundPerformance, Analysis page calls. FO DataTable title restored. Code audit: 83/84 features verified. | Dev
v5.287 | 2026-05-10 | Feature | F111 | Email login screen replaces Google OAuth (Error 400). Email as portfolio key. Auto-skip if session exists. | Dev
v5.287 | 2026-05-10 | Fix | Audit | Sprint Board corrected — all 16 items were already done in code. Only F048 genuinely missing. | Dev
v5.287 | 2026-05-10 | Docs | F112-F126 | Roadmap extended with 15 new features: SIP calc, Goal tracker, Tax P&L, AI insights, PDF export, PWA. | Dev
v5.295 | 2026-06-02 | Fix | F113 | Login screen no longer bypassed. useEffect timing bug fixed. New users → setup, returning → load. | Dev
v5.294 | 2026-06-02 | Feature | F112 | Google sign-in hardcoded Client ID on front page. No console setup needed for user. | Dev
v5.289 | 2026-06-02 | Feature | F114 | Google Drive sync: list folders, root option, create folder, save/load per-portfolio JSON. | Dev
v5.287 | 2026-06-02 | Feature | F111 | Email login screen on startup. Auto-skip for returning users. Portfolio key = email. | Dev
Roadmap | 2026-06-02 | Docs | Commercial | Full commercial roadmap added: v6.0 backend, admin dashboard, cloud DB, advisor portal, mobile app, billing. | PM

## 🗺 Roadmap
MF ADVISOR — DEVELOPMENT ROADMAP
v6.9 baseline · 100% open-source · no API keys · no subscription · local-first persistence
Phase / Version | Theme | Description | Status | Notes
DELIVERED
v5.272-287 | Foundation, Import, Returns, Tables | Multi-format import, FMT engine, scheme mapping, return-basis, compare, email login. | Completed | 80+ features.
v6.0 | Persistence, Open-Source & Admin | Critical persistence fix, IndexedDB durability, key-free auth, Admin Console with the in-app Feature DB. | Completed
v6.1 | Planning · Tax · Insights · Reports · Sync | SIP/SWP/Goal planning, FIFO STCG/LTCG tax, allocation & concentration, local+optional-AI insights, PDF/digest reports, scheduled folder backup, optional self-hosted sync, offline SW, touch charts, Help↔Settings links. | Completed | This release — all previously-pending items delivered.
FUTURE (open-source, no keys)
v6.2 | Holdings enrichment | If an open holdings/portfolio-disclosure dataset becomes available, upgrade category allocation to true stock-sector weights and exact fund overlap. | Pending | Blocked only by open data availability.
v6.3 | Goals & alerts | Multiple named goals with progress tracking; local rebalancing alerts when allocation drifts past thresholds. | Pending | Pure client-side.
v6.6 | Holdings-level allocation | If an open fund-holdings dataset becomes available, replace modeled sector/cap weights with true stock-level allocation and exact overlap. | Pending | Blocked only by open data availability.