## 📋 Feature Registry
MF ADVISOR — FEATURE REGISTRY
v5.273 audit · 2026-03-23 · 69 features tracked
ID | Category | Feature | Status | Priority | Ver Added | Target | Effort | Description | Notes / Why
F001 | Data Import | CAMS CAS .xls import | Completed | High | v5.0 | v5.0 | M | Parse CAMS Consolidated Account Statement .xls | parseXLS() present. Core parser working.
F002 | Data Import | Folio separator row fix | Completed | High | v5.273 | v5.273 | S | Skip '--' separator rows in multi-folio CAS imports | FIXED v5.273: rawBalCheck/rawMVCheck guard re-added to parseXLS().
F003 | Data Import | CAMS Transaction XLSX import | Completed | High | — | v5.276 | M | Import newer CAMS XLSX export format | DONE v5.276: parseCAMSXlsxRows. Auto-detected via detectFormat().
F004 | Data Import | CAMS Current Value XLSX import | Completed | Medium | — | v5.281 | M | Verify multi-folio balances via CAMS CV export | DONE v5.281: parseCAMSCurrentValue() auto-detects CAMS Current Value XLSX via cams_cv format code. Seeds holdings as snapshot rows. Wire through parseAnyFile.
F005 | Data Import | KFintech XLSX import | Completed | Medium | — | v5.276 | M | Import KFintech transaction exports directly | DONE v5.276: parseKFintechRows. Auto-detected via detectFormat().
F006 | Data Import | Generic CSV import | Completed | Low | — | v5.276 | S | Fallback CSV parser for any tabular export | DONE v5.276: parseGenericCSV. Handles Date/Scheme/Type CSV.
F007 | Data Import | Auto format detection | Completed | Medium | — | v5.276 | S | Auto-detect CAMS/KFintech/CSV format from headers | DONE v5.276: parseAnyFile routes by extension + header detection.
F008 | Data Import | Incremental XLS append (dedup) | Completed | High | v5.273 | v5.273 | S | Append new transactions from XLS without duplicates | FIXED v5.273: appendXLS callback + Append XLS button in Data Management.
F009 | Data Import | Bulk upload transactions CSV | Completed | Medium | v5.272 | v5.272 | M | Upload CSV of transactions with deduplication | bulkUploadTransactionsCSV present.
F010 | Data Import | JSON backup export & import | Completed | High | v5.0 | v5.0 | M | Full backup/restore including NAV cache and settings | saveToJSON and loadFromFile both working.
F011 | Data Import | Folder/directory auto-save | Completed | Medium | v5.1 | v5.1 | L | Auto-save to user-chosen folder on every change | File System Access API. Chrome/Edge only.
F012 | Scheme Mapping | Auto-map via ISIN | Completed | High | v5.0 | v5.0 | M | Use ISIN for fast accurate fund identification | ISIN lookup against AMFI master.
F013 | Scheme Mapping | AMC locking in matchScore | Completed | Critical | v5.272 | v5.272 | M | Prevent cross-AMC mismatches (ABSL→Edelweiss etc) | AMC_LOCK table. Fixed 7 wrong mappings.
F014 | Scheme Mapping | ABSL search query expansion | Completed | High | v5.272 | v5.272 | S | Expand ABSL prefix before MFAPI search | Prevents wrong AMC results for ABSL funds.
F015 | Scheme Mapping | Inline edit — Search & Pick | Completed | High | v5.272 | v5.272 | L | Per-row live search dropdown in Settings | smEditRow/smEditSearch/smEditPick working.
F016 | Scheme Mapping | Stale NAV cleared on remap | Completed | High | v5.272 | v5.272 | S | Delete old wrong NAV immediately on remap | smEditPick deletes navByScheme before re-fetch.
F017 | Scheme Mapping | Name confirmed from MFAPI | Completed | Medium | v5.272 | v5.272 | S | Update amfiName from MFAPI meta after each pick | d.meta.scheme_name used on every pick/apply.
F018 | Scheme Mapping | Per-row re-fetch NAV (⟳) | Completed | Medium | v5.272 | v5.272 | S | Re-fetch NAV and confirm name for one scheme | ⟳ button per row in Scheme Mapping table.
F019 | Scheme Mapping | Refresh All NAV | Completed | Medium | v5.272 | v5.272 | S | Clear and re-fetch NAV for all mapped schemes | Refresh All NAV button in Scheme Mapping card.
F020 | Scheme Mapping | Bulk upload mapping CSV | Completed | High | v5.272 | v5.272 | M | Upload CSV of Scheme Name/AMFI Code in bulk | bulkUploadSchemeMapping. Clears and re-fetches NAV.
F021 | Scheme Mapping | Skip exited funds | Completed | Medium | — | v5.276 | S | Auto-skip zero-unit schemes; 'skip (exited)' button | DONE v5.276: Skip (exited) button; wrapped in Fragment to fix adjacent JSX crash.
F022 | Multi-Currency | FMT() replaces INR() everywhere | Completed | Critical | v5.273 | v5.273 | L | All monetary values respect selected currency | FIXED v5.273: All 55 INR() calls replaced with FMT(). Dashboard, FY Summary, XIRR Review, NPV, Fund Overview now fully currency-aware.
F023 | Multi-Currency | Currency selector UI | Completed | Medium | v5.1 | v5.1 | S | Currency toggle in header and Settings | Buttons update G_CURRENCY correctly.
F024 | Multi-Currency | Display unit (Cr/L/K) | Completed | Low | v5.1 | v5.1 | S | Toggle between Crores/Lakhs/thousands | G_UNIT and DISPLAY_UNITS respected by FMT().
F025 | Dashboard | Portfolio value KPI card | Completed | Critical | v5.273 | v5.273 | S | Hero card shows current portfolio value in selected currency | FIXED v5.273: INR()→FMT(). Currency switch now works.
F026 | Dashboard | Unrealised gain KPI card | Completed | High | v5.273 | v5.273 | S | Hero card shows unrealised gain in selected currency | FIXED v5.273: INR()→FMT().
F027 | Dashboard | Invested / Net deployed cards | Completed | High | v5.273 | v5.273 | S | Hero cards in selected currency | FIXED v5.273: INR()→FMT() on both cards.
F028 | Dashboard | Portfolio timeline chart | Completed | High | v5.0 | v5.0 | L | Area/line chart corpus vs benchmarks over time | Working. Y-axis labels now use FMT().
F029 | Dashboard | Top 5 / Bottom 5 by XIRR | Completed | Medium | v5.0 | v5.0 | M | Ranked fund cards by XIRR | Fund values now use FMT().
F030 | Dashboard | Portfolio recommendations | Completed | Medium | v5.0 | v5.0 | L | Rules-based recommendations using XIRR/Sharpe/Alpha | Working.
F031 | Dashboard | FY Summary collapsible card | Completed | Low | v5.2 | v5.2 | M | FY breakdown accessible from Dashboard | CollapsibleCard present.
F032 | Dashboard | NAV date in portfolio value card | Completed | Low | — | v5.275 | S | Show exact NAV date in portfolio value card sub-label | DONE v5.275: navAsOf() shows 'NAV current' or 'NAV N days old' in Portfolio Value card sub-label.
F033 | Analysis | Fund Overview table | Completed | High | v5.0 | v5.0 | L | Filterable table with full fund metrics | All monetary columns now use FMT().
F034 | Analysis | Fund Performance page | Completed | High | v5.0 | v5.0 | L | Per-fund NAV % return vs benchmarks | Working.
F035 | Analysis | FY Summary page — currency | Completed | High | v5.273 | v5.273 | M | All FY Summary monetary values in selected currency | FIXED v5.273: 19 INR()→FMT() in FYSummaryPage.
F036 | Analysis | XIRR Review — currency | Completed | High | v5.273 | v5.273 | M | XIRR Review chart and table in selected currency | FIXED v5.273: INR()→FMT() in XirrReviewPage and XIRRHistoryChart.
F037 | Analysis | Analysis page (Sharpe/Beta/Alpha) | Completed | High | v5.0 | v5.0 | L | Risk-adjusted metrics with rolling calculations | Working.
F038 | Analysis | NPV page — currency | Completed | Medium | v5.273 | v5.273 | M | NPV table and chart in selected currency | FIXED v5.273: INR()→FMT() in NpvPage.
F039 | Analysis | Validation panel | Completed | High | v5.273 | v5.273 | M | Check duplicates, missing NAV, future dates, NAV mismatch | FIXED v5.273: runValidation (6 rules) + 🔍 button in Data Management + filterable results panel with Dismiss/Re-run.
F040 | Analysis | Group by AMC/class/status | Completed | Medium | v5.272 | v5.272 | M | Group fund rows in Overview and Performance | groupBy lifted to App, DataTable supports headers.
F041 | Analysis | Show/hide exited funds (filter) | Completed | High | v5.273 | v5.273 | S | Exited fund toggle filters all page calculations | FIXED v5.273: filteredEnabledSet useMemo added in App. Passed to all 7 page components instead of raw enabledSet.
F042 | Analysis | Multi-portfolio compare page | Completed | Low | — | v5.282 | XL | Side-by-side value/XIRR/gain across portfolios | DONE v5.282: PortfolioComparePage — tab auto-appears when 2+ portfolios. Cards + table. Respects returnBasis. Loads from _store without switching.
F043 | Help & Docs | Help page structure | Completed | Medium | v5.2 | v5.2 | M | 4-tab help page: FAQ, User Manual, Technical, Changelog | Structure present and working.
F044 | Help & Docs | FAQ content | Completed | Medium | v5.2 | v5.2 | M | Answers to common user questions | 10 FAQ entries.
F045 | Help & Docs | User Manual content | Completed | Medium | v5.2 | v5.276 | M | Step-by-step guides for all features | DONE v5.276: Getting Started + Settings sections updated.
F046 | Help & Docs | Technical reference / formulas | Completed | Low | v5.2 | v5.276 | L | Formula documentation for XIRR, Sharpe, Alpha etc | DONE v5.276: Glossary of Terms added to Technical tab (12 definitions).
F047 | Help & Docs | Changelog in Help page | Completed | Low | v5.2 | v5.276 | S | Version history | DONE v5.276: Changelog entries for v5.276, v5.275, v5.274, v5.273.
F048 | Help & Docs | Cross-links Help↔Settings | Completed | Low | — | v5.276 | S | Links from Help to relevant Settings sections | DONE v5.276: Getting Help section with cross-links added.
F049 | Settings | Dataset status banner | Completed | Medium | v5.272 | v5.272 | S | Txn/scheme/mapped/NAV counts at top of Settings | Working.
F050 | Settings | Header transaction chip | Completed | Low | v5.272 | v5.272 | S | Live txn count in app header | Working.
F051 | Settings | Clear & New Analysis (confirm) | Completed | Medium | v5.272 | v5.272 | S | Confirm dialog before wiping all data | Working.
F052 | Settings | Add Transaction + NAV auto-fetch | Completed | Medium | v5.272 | v5.272 | S | Auto-fetch NAV after Add Transaction | Working.
F053 | Settings | Scheme Mapping review table | Completed | High | v5.272 | v5.272 | L | Full inline-edit table with search, re-fetch, clear | Working.
F054 | Settings | Append XLS Transactions button | Completed | High | v5.273 | v5.273 | S | Append XLS button in Data Management | FIXED v5.273: appendXLS callback + button added.
F055 | NAV | NAV auto-refresh interval | Completed | Medium | v5.0 | v5.0 | M | Configurable background refresh of latest NAV | Working.
F056 | NAV | NAV staleness date display | Completed | Low | — | v5.275 | S | Exact NAV date in portfolio value card | DONE v5.275: navAsOf() covers staleness. Portfolio Value sub-label updates dynamically.
F057 | NAV | lastBusinessDay NAV cap | Completed | Medium | v5.272 | v5.272 | S | Cap period end to last business day | lastBusinessDay() present.
F058 | NAV | Benchmark comparison | Completed | High | v5.0 | v5.0 | L | Nifty 50 and custom benchmarks vs portfolio | Working.
F059 | NAV | PPF equivalent benchmark | Completed | Medium | v5.0 | v5.0 | M | Synthetic PPF corpus from same cash flows | Working.
F060 | UX | Multi-user profiles | Completed | Medium | v5.1 | v5.1 | L | Separate saved states per user | Working.
F061 | UX | Period picker (1M–All) | Completed | High | v5.0 | v5.0 | S | Period filter shared across all pages | Working.
F062 | UX | Export HTML / Word / Print | Completed | Medium | v5.1 | v5.1 | L | Full report export | Working.
F063 | UX | PWA installable | Completed | Low | v5.1 | v5.1 | M | Add to Home Screen on Android/iOS | Working.
F064 | UX | Edge Tracking Prevention fix | Completed | Critical | v5.272 | v5.272 | M | Works in Edge when localStorage blocked | _store wrapper with memory fallback.
F065 | UX | Loading screen Start Fresh | Completed | High | v5.272 | v5.272 | S | 5s safety timeout + escape button | Prevents permanent blank screen.
F066 | UX | Term definitions glossary | Completed | Low | v5.0 | v5.276 | M | 15 metric definitions in Fund Overview | DONE v5.276: Glossary accessible from Technical tab in Help.
F067 | UX | Multi-portfolio system | Completed | Low | — | v5.281 | XL | Multiple named portfolio profiles | DONE v5.281: Users renamed to Portfolios throughout — header badge, Portfolio Manager modal, add/delete/switch copy, default name.
F068 | UX | Root-level error boundary | Completed | Medium | — | v5.275 | S | Catch App-level crashes gracefully | DONE v5.275: RootErrorBoundary class wraps createRoot(). App crashes show error + Reload button.
F069 | UX | Blank screen prevention | Completed | Critical | v5.272 | v5.273 | L | No Babel parse errors, no literal newlines in JS | Fixed multiple issues across v5.272-273.
F070 | Display Format | Flexible format engine (applyFMT/customFmt) | Completed | Critical | v5.274 | v5.274 | L | Full format engine replacing old FMT(). Currency×rate, auto/manual scale, decimals 0-4, neg style, separator, zero display. | FIXED v5.274: applyFMT() reads G_FMT global. customFmt() parses Excel-style strings. Old duplicate FMT/G_CURRENCY declarations removed — was the blank-screen cause.
F071 | Display Format | Format presets (6 one-click) | Completed | High | v5.274 | v5.274 | S | 6 presets: ₹ Auto, ₹ Lakhs, ₹ Crores, ₹ Full, $ Millions, € Millions. | FIXED v5.274: FMT_PRESETS array. Clicking a preset calls applyDisplayFmt() syncing state + G_FMT global.
F072 | Display Format | Live preview in Settings | Completed | High | v5.274 | v5.274 | S | Shows formatted output of ₹1,23,45,678.50 updating instantly as controls change. | FIXED v5.274: Preview row in format panel calls applyFMT(12345678.5, displayFmt) reactively.
F073 | Display Format | Fine controls: currency, scale, decimals, neg, sep, zero | Completed | High | v5.274 | v5.274 | M | 6 independent controls in 3-column grid. All update displayFmt state and G_FMT global immediately. | FIXED v5.274: Currency+Scale as dropdowns, Decimals/Neg/Thousands/Zero as pill button groups.
F074 | Display Format | Custom format string (Excel-style) | Completed | High | v5.274 | v5.274 | M | Custom format string shown when scale=custom. Parses prefix+#,##0.00+suffix pattern. | FIXED v5.274: customFmt() supports ₹#,##0.00, #,##0 Cr, (#,##0), etc.
F075 | Display Format | Editable exchange rates | Completed | Medium | v5.274 | v5.274 | S | User enters own FX rates (1 INR=X) for USD/EUR/GBP/AED/SGD in collapsible section. | FIXED v5.274: Rates stored in displayFmt.rates. applyFMT reads rates[currency] first, falls back to CURRENCIES[].rate.
F076 | Display Format | SGD and GBP added | Completed | Low | v5.274 | v5.274 | S | Singapore Dollar and British Pound added. Total 6 currencies: INR, USD, EUR, GBP, AED, SGD. | FIXED v5.274: CURRENCIES object extended.
F077 | Display Format | Header format badge (replaces dropdown) | Completed | Medium | v5.274 | v5.274 | S | Compact badge shows current format (e.g. ₹.00 or $M.00). Clicking opens Settings. | FIXED v5.274: Old <select> replaced with <button> showing sym+scale+decimals pattern.
F078 | Display Format | displayFmt persisted in JSON backup | Completed | Medium | v5.274 | v5.274 | S | All format settings saved in JSON backup and restored correctly on load. | FIXED v5.274: displayFmt in saveState. Restore sets state + G_FMT/G_CURRENCY/G_UNIT globals.
F079 | Bug Fix | Duplicate FMT/G_CURRENCY/G_UNIT declarations removed | Completed | Critical | v5.274 | v5.274 | S | Blank screen caused by duplicate function FMT( and let G_CURRENCY= in v5.274 output. | ROOT CAUSE: new format infrastructure was ADDED on top of old block instead of replacing it. Fix: start from v5.273 clean base, replace old block in one shot, verify count=1 before deploy.
F080 | Bug Fix | displayFmt not in SettingsPage signature (blank/crash) | Completed | Critical | v5.274 | v5.274 | S | Settings page crashed with 'ReferenceError: displayFmt is not defined'. | ROOT CAUSE: deployed v5.274.html was an intermediate build — displayFmt/applyDisplayFmt were in the App call-site but NOT in SettingsPage's destructured props signature. Fix: deployed from the correct working file with both in the signature.
F081 | NAV | Incremental NAV fetch (skip current, append missing only) | Completed | High | v5.274 | v5.274 | M | Fetch only missing NAV dates instead of re-downloading full history on every refresh. | v5.274: fetchNavBackground now: (1) skips schemes whose last NAV date ≥ last business day (zero API calls); (2) uses /mf/{code}/latest for stale schemes that have existing data — appends only new entries; (3) falls back to full /mf/{code} only when no data exists. Logs 'NAV: N updated, M already current' to console.
F082 | NAV | Separate NAV cache (mfa_nav_v1_{user}) | Completed | High | v5.275 | v5.275 | M | NAV history stored in its own _store key — removed from main state blob. | v5.275: saveNavCache/loadNavCache helpers. Startup loads from cache key first. Auto-persists on navByScheme state change. Cleared on reset and user-switch.
F083 | NAV | Parallel NAV fetch (5 concurrent) | Completed | High | v5.275 | v5.275 | M | 5 schemes fetched concurrently via Promise.all — ~5x faster than sequential. | v5.275: fetchOne() per scheme, batched Promise.all(CONCURRENCY=5). UI and cache flushed after each batch for live progress.
F084 | NAV | Incremental NAV (/latest endpoint) | Completed | High | v5.275 | v5.275 | S | Stale schemes use /mf/{code}/latest (small payload) instead of full re-download. | v5.275: Three tiers — skip current, /latest if stale with data, full fetch if empty. 95%+ less data on daily refreshes.
F085 | UX | Root-level error boundary | Completed | Medium | v5.275 | v5.275 | S | App-level crashes show error panel + Reload button instead of blank screen. | v5.275: RootErrorBoundary class component. Wraps ReactDOM.createRoot render. Uses _store.remove not localStorage on reload.
F086 | Bug Fix | returnBasis not in DashboardPage scope — blank screen fix | Completed | Critical | v5.277 | v5.277 | S | returnBasis was used inside DashboardPage JSX but never declared in its props — ReferenceError at render. | ROOT CAUSE: Changes were applied to file but DashboardPage signature + call site were not updated together. Fix: start from v5.276 clean base, apply all 13 changes atomically with assertion checks before saving.
F087 | Analysis | Return basis selector (Book Cost / Net Deployed / Gross Invested) | Completed | High | v5.277 | v5.277 | M | Toggle on Dashboard above hero cards and in Settings → Display Format. Default: Book Cost (FIFO). | v5.277: returnBasis state in App. Passed to DashboardPage (sig + call) and SettingsPage (sig + call). Persisted in JSON backup. Restored on load.
F088 | Analysis | heroStats: all three gain bases computed every render | Completed | High | v5.277 | v5.277 | M | gain_net, gain_book, gain_gross and matching gainPct always available. | v5.277: totalBookCost = sum of FIFO costBasis across all enabled schemes. gain=returnBasis determines which value is the primary 'gain' shown. returnBasis in useMemo deps.
F089 | Dashboard | Hero cards expanded: 6 cards showing all perspectives | Completed | High | v5.277 | v5.277 | S | Portfolio Value, Gross Invested, Redeemed, Net Deployed, Book Cost (FIFO), Gain vs selected basis. | v5.277: Old 3-card layout (Invested, Net Deployed, Unrealised Gain) replaced. Gain card label is dynamic: 'Gain vs Book Cost' / 'Gain vs Net Deployed' / 'Gain vs Gross Invested'.
F090 | Settings | Return Calculation Basis explanation in Settings | Completed | Medium | v5.277 | v5.277 | S | Plain-language description of all three bases in Settings → Display Format card. | v5.277: Section added below Exchange Rates expander. Explains why Net Deployed can mislead.
F091 | Analysis | Fund Overview: returnBasis-aware Abs Return % | Completed | High | v5.278 | v5.278 | M | Abs Return % denominator changes with return basis: Book Cost, Net Deployed, or Gross Invested. | v5.278: rpDenom computed from returnBasis in FundOverview per-fund loop and totals row. Column header updates dynamically: 'Abs Return % (vs Book Cost)' etc. returnBasis passed via prop. ¦ v5.285: returnBasis now correctly passed in FundOverviewPage JSX call (was missing from call site).
F092 | Analysis | fundStats: costBasis, returnPct, unrealisedGain, realizedGain per fund | Completed | High | v5.278 | v5.278 | M | fundStats useMemo extended to compute FIFO cost metrics for every fund on every render. | v5.278: computeFIFO() called per fund in fundStats. totalReturn = unrealisedGain + realizedGain. returnPct uses same rpDen logic as FundOverview. returnBasis added to fundStats deps.
F093 | Analysis | FY Summary: Gain vs Net and Gain % columns | Completed | Medium | v5.278 | v5.278 | S | FY Summary table adds two new columns: Gain vs Net Invested at FY-end, and Gain %. | v5.278: hdrs extended with Gain vs Net and Gain %. rows array computes gain_fy and gainPct_fy from running net invested at each financial year end.
F094 | Analysis | XIRR + NPV intentionally unaffected by return basis | Completed | Low | v5.278 | v5.278 | S | XIRR and NPV use actual cash flows — not a cost basis. They are always basis-independent. | Design decision: XIRR = time-weighted efficiency of money deployed. NPV = discounted cash flows. Neither should change with cost basis selection. Only gain% metrics change.
F095 | UX | Return Basis selector in global top header | Completed | High | v5.279 | v5.279 | S | Book / Net / Gross pill always visible on every page in the top nav bar. | v5.279: Compact 3-button pill added to the right-side header row next to the format badge. Clicking instantly re-computes all basis-aware metrics on the current page. Removed duplicate toggle from inside Dashboard hero cards.
F096 | Dashboard | DashboardPage wired: returnBasis in sig + call | Completed | High | v5.279 | v5.279 | S | DashboardPage now correctly receives returnBasis/setReturnBasis as props. | v5.279: Fixed the root cause of v5.277 ReferenceError — DashboardPage sig and call both now include returnBasis and setReturnBasis.
F097 | Analysis | FYSummaryPage: returnBasis wired (Gain % column) | Completed | Medium | v5.279 | v5.279 | S | FY Summary Gain % column uses returnBasis denominator when available. | v5.279: returnBasis passed to FYSummaryPage sig + call. gain_fy uses runningNet. Column headers clarified: 'Gain vs Net Invested' and 'Gain % (vs Net)'.
F098 | Analysis | AnalysisPage: returnBasis wired (fund returnPct) | Completed | Medium | v5.279 | v5.279 | S | Analysis fund cards now show return% using selected basis. | v5.279: returnBasis passed to AnalysisPage sig + call. Fund cards show r.returnPct with basis label: '(book cost)', '(net dep)', or '(gross)'. ¦ v5.285: prop indentation fixed in JSX call.
F099 | Dashboard | Portfolio Timeline: basis-aware cost line | Completed | High | v5.280 | v5.280 | M | Chart dashed baseline changes dynamically with Return Basis selector. | v5.280: Three data series computed per tick: grossData (total invested), netData (invested−redeemed), costData (FIFO book cost of held units). Series label also updates: 'Book Cost (FIFO)' / 'Net Deployed' / 'Gross Invested'. returnBasis added to useMemo deps so chart re-renders on toggle.
F100 | Analysis | FundPerformancePage: Abs Return% column | Completed | Medium | v5.280 | v5.280 | M | Abs Return % column added to Fund Performance comparison table. Respects Return Basis. | v5.280: computeFIFO + computeInvested called per fund in rows useMemo. fpDenom = costBasis / net / grossInvested per returnBasis. Column header shows active basis. returnBasis in rows deps. ¦ v5.285: prop indentation fixed in JSX call.
F101 | Analysis | Multi-portfolio compare page | Completed | High | v5.282 | v5.282 | L | Side-by-side portfolio comparison — ⚖ Compare tab in nav, cards + table, return basis aware. | v5.282: PortfolioComparePage. Tab shows only when 2+ portfolios. Loads each portfolio from _store. 10-row comparison table + summary cards with top 3 holdings.
F102 | Bug Fix | Compare page: COLORS is not defined — crash fix | Completed | Critical | v5.283 | v5.283 | S | Compare page crashed with ReferenceError: COLORS is not defined. | ROOT CAUSE: PortfolioComparePage used 'const C=COLORS' but the app-level color palette is the global const C (defined at module top). COLORS doesn't exist. Fix: replaced with comment — C is already in scope as a module-level constant.
F103 | Perf | Portfolio Timeline chart: pre-filter txns per scheme | Completed | High | v5.283 | v5.283 | S | computeFIFO was called 180 ticks × N schemes per chart render — O(180 × N × T). | v5.283: txnsByScheme={} map pre-built once before the tick loop. computeFIFO now receives pre-filtered array instead of full sortedTxns. Reduces filtering work from 180×N×T to N×T + 180×N — ~180x fewer array scans.
F104 | UX | Fund Overview: sort + filter toolbar now visible | Completed | Medium | v5.283 | v5.283 | S | DataTable sort/filter was already implemented but toolbar only shows when title prop provided. | v5.283: DataTable in FundOverview now receives title prop — e.g. 'Returns & Value — 39 funds'. Toolbar with Filters toggle and CSV download now visible. Click any column header to sort. Filter row appears on toggle.
F105 | Analysis | Funds to Add: refreshed Apr 2025 with Sortino + entry context | Completed | High | v5.283 | v5.283 | M | Recommendations updated with Apr 2025 data — Sortino-ranked, entry-point context, AMFI codes. | v5.283: 5 updated recommendations: Navi Nifty 50 (0.06% TER, Sortino 1.4), Parag Parikh (Sortino 1.6, down 12% from high), Motilal Midcap (32% 3Y XIRR, Sortino 1.8, down 22%), Nippon Small Cap (Sortino 1.3), HDFC Short Duration (rate cut cycle play). Each shows AMFI code + mfapi.in link for direct import.
F106 | Bug Fix | FY+XIRR tables: no render props / no hook-in-arg (blank screen fix) | Completed | Critical | v5.284 | v5.284 | S | Previous attempts caused blank screen (useMemo in fn arg) and raw code dump (arrow fn render props in JSX). | v5.284: All new DataTable columns use pre-formatted string values — no render props needed. XIRR table data computed inline with plain new Date() — no extra hooks. FY col defs placed inside JSX attributes using function() syntax, no arrow fns with JSX returns.
F107 | UX | FY Summary: DataTable sort/filter on main table and fund drill-down | Completed | Medium | v5.284 | v5.284 | M | FY Summary now uses DataTable for both the yearly table and the per-fund drill-down. | v5.284: Main table columns: FY, Invested, Redeemed, Dividends, Net Flow, Portfolio at FY End, Gain vs Net, Gain %. Fund drill-down: Fund, Invested, Redeemed, Net, Txns. Sort by any column, filter by text.
F108 | UX | XIRR Review: per-fund All-Time + Period XIRR sortable table | Completed | Medium | v5.284 | v5.284 | M | New sortable per-fund table below XIRR chart with All-Time and Period XIRR. | v5.284: Computed inline per row — no new hooks. Shows fund name, current value, All-Time XIRR, Period XIRR. Sort by XIRR descending to find best/worst performers. Filter by fund name.
F109 | Fix | Full code audit: 83/84 features verified in code (v5.285) | Completed | High | v5.285 | v5.285 | S | Systematic code audit confirmed 83 of 84 checked features present. One false-positive (INR( in changelog string). | v5.285 audit findings: (1) FundOverviewPage missing returnBasis in JSX call — fixed. (2) FundPerformancePage + AnalysisPage had wrong prop indentation — fixed. (3) FO DataTable title was missing — restored. (4) DataTable confirmed to have full sort (sortKey state, clickable headers) and filter. (5) returnBasis now correctly wired to all 6 key pages: Dashboard, FO, FP, FY, Analysis, Settings.

## 📊 Status Summary
MF ADVISOR — STATUS SUMMARY
v5.273 · Generated 2026-03-23
OVERALL STATUS
Status | Count | % of Total | Visual
Completed | 109 | 100% | ██████████████████████████████ 109/109
In Progress | 0 | 0% | 0/109
Minor Update Needed | 0 | 0% | 0/109
Not Working | 0 | 0% | 0/109
Pending | 0 | 0% | 0/109
Won't Fix | 0 | 0% | 0/109
TOTAL | 109 | 100%
BY CATEGORY
Category | Total | Done | Minor | Not Working | Pending | % Done | Health
Analysis | 10 | 9 | — | — | 1 | 90% | ██████████████░
Dashboard | 8 | 7 | 1 | — | — | 87.5% | █████████████░░
Data Import | 11 | 6 | — | — | 5 | 54.55% | ████████░░░░░░░
Help & Docs | 6 | 2 | 3 | — | 1 | 33.33% | █████░░░░░░░░░░
Multi-Currency | 3 | 3 | — | — | — | 100% | ███████████████
NAV | 5 | 4 | 1 | — | — | 80% | ████████████░░░
Scheme Mapping | 10 | 9 | — | — | 1 | 90% | ██████████████░
Settings | 6 | 6 | — | — | — | 100% | ███████████████
UX | 10 | 7 | 1 | — | 2 | 70% | ██████████░░░░░

## 🎯 Sprint Board
MF ADVISOR — SPRINT / PRIORITY BOARD
Open items sorted by priority · Edit Sprint and Assigned To columns
ID | Category | Feature | Status | Priority | Effort | Sprint | Assigned To | Notes / Blocker
F003 | Data Import | CAMS Transaction XLSX import | Pending | High | M |  |  | parseCAMSXlsxRows was in v5.262 rebuild. Needs safe re-grafting onto v5.273.
F004 | Data Import | CAMS Current Value XLSX import | Pending | Medium | M |  |  | parseCAMSCurrentValue coded in rebuild. Not yet in v5.273.
F005 | Data Import | KFintech XLSX import | Pending | Medium | M |  |  | parseKFintechRows coded. Not yet in v5.273.
F007 | Data Import | Auto format detection | Pending | Medium | S |  |  | parseAnyFile coded in rebuild. Not yet in v5.273.
F045 | Help & Docs | User Manual content | Minor Update Needed | Medium | M |  |  | Does not cover: bulk CSV, inline remapping, appendXLS, validation panel (all new in v5.272-273).
F021 | Scheme Mapping | Skip exited funds | Pending | Medium | S |  |  | Written in v5.262 but not yet in v5.273.
F068 | UX | Root-level error boundary | Pending | Medium | S |  |  | Only page-level ErrorBoundary wrappers exist.
F042 | Analysis | Multi-portfolio compare page | Pending | Low | XL |  |  | Large feature. Needs stable v5.273 base first.
F032 | Dashboard | NAV date in portfolio value card | Minor Update Needed | Low | S |  |  | navAsOf()/navDaysStale not yet added. Sub-label still hardcoded.
F006 | Data Import | Generic CSV import | Pending | Low | S |  |  | parseGenericCSV coded. Low priority.
F046 | Help & Docs | Technical reference / formulas | Minor Update Needed | Low | L |  |  | Sparse. TERM_DEFS (15 terms) not linked from Help tab.
F047 | Help & Docs | Changelog in Help page | Minor Update Needed | Low | S |  |  | Does not reflect v5.272-273 changes.
F048 | Help & Docs | Cross-links Help↔Settings | Pending | Low | S |  |  | None currently.
F056 | NAV | NAV staleness date display | Minor Update Needed | Low | S |  |  | navAsOf()/navDaysStale not yet added.
F066 | UX | Term definitions glossary | Minor Update Needed | Low | M |  |  | Not linked from Help. Needs new metrics added.
F067 | UX | Multi-portfolio system | Pending | Low | XL |  |  | Large feature. Stable base needed first.

## 🐛 Bug Tracker
MF ADVISOR — BUG & ISSUE TRACKER
Known issues · root causes · fixes applied
Bug ID | Feature ID | Category | Title | Status | Severity | Root Cause | Fix Applied | Ver Fixed | Reported
B001 | F022-F038 | Multi-Currency | INR() hardcoded in 55+ JSX call sites — currency switch had no effect | Fixed | Critical | FMT() existed but only 17 of 72 call sites used it. Dashboard hero cards, FY Summary, XIRR Review, NPV all used INR(). | v5.273: Replaced all INR() with FMT() via regex pass. Verified 0 INR() calls remain. | v5.273 | 2024-03-22
B002 | F041 | Analysis | Show/hide exited: filteredEnabledSet missing — exited funds still in calculations | Fixed | High | showExited filtered sidebar list only. enabledSet (unfiltered) was passed to all 7 page components. Exited funds affected all calculations. | v5.273: filteredEnabledSet useMemo added in App. When showExited=false, filters out exited fund names. Passed to all 7 pages. | v5.273 | 2024-03-22
B003 | F002 | Data Import | Folio separator rows included in transaction list (multi-folio CAS) | Fixed | High | rawBalCheck/rawMVCheck guard was in v5.262 parseXLS() but dropped in revert to v5.113 base. | v5.273: Re-added 2-line folio separator check (rawBalCheck==='--' && rawMVCheck==='--') in parseXLS() row loop. | v5.273 | 2024-03-22
B004 | F008 | Data Import | No way to append new XLS transactions without full re-import | Fixed | High | appendXLS callback was in v5.262 but dropped. Users had to re-import entire file or add transactions one by one. | v5.273: appendXLS useCallback re-added. Deduplicates by date¦scheme¦type¦amount key. Button added in Data Management. | v5.273 | 2024-03-22
B005 | F039 | Settings | No validation of transaction data | Fixed | High | runValidation with 6 rules was in v5.262 rebuild but absent in v5.272. Users had no way to spot duplicates or missing NAV. | v5.273: runValidation (6 rules: future dates, missing amount, no NAV, NAV mismatch >10%, duplicates, missing scheme). Panel with filter/dismiss/re-run in Data Management. | v5.273 | 2024-03-22
B006 | F025 | Dashboard | Dashboard KPI hero cards showed ₹ regardless of currency setting | Fixed | Critical | heroStats.pv, heroStats.gain, heroStats.invested, heroStats.net all rendered via INR() in DashboardPage JSX. | v5.273: All INR() replaced with FMT() globally. Hero cards now respect G_CURRENCY. | v5.273 | 2024-03-22
B007 | F035 | Analysis | FY Summary page monetary values hardcoded in ₹ | Fixed | High | FYSummaryPage had 19 INR() calls for invested, redeemed, dividends, net flow, portfolio value. | v5.273: All 19 INR()→FMT() replaced. | v5.273 | 2024-03-22
B008 | F036 | Analysis | XIRR Review chart tooltips and table used hardcoded ₹ | Fixed | High | XirrReviewPage and XIRRHistoryChart both used INR(). 5 INR() calls in chart tooltip builder strings. | v5.273: All INR()→FMT() replaced. | v5.273 | 2024-03-22
B009 | F038 | Analysis | NPV page values hardcoded in ₹ | Fixed | Medium | NpvPage used INR() for NPV display and chart Y-axis. | v5.273: INR()→FMT() replaced. | v5.273 | 2024-03-22
B010 | F032 | Dashboard | NAV date not shown in Portfolio Value card | Open | Low | navAsOf()/navDaysStale not yet added. Sub-label hardcoded to 'Current market value'. | Planned for v5.274: Add navAsOf() function and navDaysStale useMemo in DashboardPage. | — | 2024-03-22
B011 | F069 | UX | Babel blank screen — literal newline in JS string | Fixed | Critical | join('\n') written with real newline inside single-quoted string. Babel: Unterminated string constant. | v5.272: Changed to join('\\n'). Added automated literal-newline scan before deploy. | v5.272 | 2024-03-21
B012 | F064 | UX | Edge Tracking Prevention blocked localStorage → blank screen | Fixed | Critical | Edge blocks localStorage on file:// protocol. Every _store.get() returned null, app stuck in 'loading' state. | v5.272: _store wrapper tries localStorage, falls back to in-memory Map. | v5.272 | 2024-03-22

## 📝 Change Log
MF ADVISOR — CHANGE LOG
History of all changes by version
Version | Date | Type | Feature ID | Change | Author
v5.273 | 2024-03-23 | Fix | F022 | Replaced all 55 INR() calls with FMT() — currency now works on Dashboard, FY Summary, XIRR Review, NPV, Fund Overview | Dev
v5.273 | 2024-03-23 | Fix | F041 | Added filteredEnabledSet in App — show/hide exited funds now filters all page calculations, not just sidebar list | Dev
v5.273 | 2024-03-23 | Fix | F002 | Re-added folio separator fix in parseXLS() — rawBalCheck/rawMVCheck guard skips '--' rows in multi-folio CAS | Dev
v5.273 | 2024-03-23 | Feature | F008 | appendXLS callback added — import more transactions from XLS with deduplication | Dev
v5.273 | 2024-03-23 | Feature | F054 | Append XLS Transactions button added to Data Management card | Dev
v5.273 | 2024-03-23 | Feature | F039 | runValidation added — 6 rules (future dates, missing amounts, no NAV, NAV mismatch, duplicates). Panel with filter/dismiss/re-run in Settings. | Dev
v5.272 | 2024-03-22 | Fix | F013 | AMC_LOCK in matchScore — prevents cross-AMC mismatches (ABSL→Edelweiss, Nippon→Invesco etc) | Dev
v5.272 | 2024-03-22 | Feature | F015 | Inline scheme mapping edit with live MFAPI search dropdown per row | Dev
v5.272 | 2024-03-22 | Fix | F016 | smEditPick clears old navByScheme entry before re-fetch | Dev
v5.272 | 2024-03-22 | Feature | F019 | Refresh All NAV button — re-fetches NAV for all mapped schemes at once | Dev
v5.272 | 2024-03-22 | Feature | F020 | bulkUploadSchemeMapping — CSV upload for scheme/AMFI code mapping in bulk | Dev
v5.272 | 2024-03-22 | Feature | F009 | bulkUploadTransactionsCSV — CSV upload for transactions with deduplication | Dev
v5.272 | 2024-03-22 | Feature | F049 | Dataset status banner at top of SettingsPage | Dev
v5.272 | 2024-03-22 | Fix | F064 | _store wrapper — Edge Tracking Prevention fix, falls back to in-memory storage | Dev
v5.272 | 2024-03-22 | Fix | F065 | Loading screen: 5-second safety timeout + Start Fresh button | Dev
v5.272 | 2024-03-22 | Fix | B011 | join('\n') literal newline in Babel script fixed — was causing silent crash → blank screen | Dev
v5.1 | 2024-01-01 | Feature | F011 | Folder/directory auto-save via File System Access API | Dev
v5.1 | 2024-01-01 | Feature | F060 | Multi-user profiles | Dev
v5.1 | 2024-01-01 | Feature | F062 | Export HTML, Word, Print | Dev
v5.0 | 2023-06-01 | Feature | F001 | Initial release: CAMS import, Dashboard, Fund Overview, Performance, FY Summary, XIRR, Analysis, NPV, Settings, Help | Dev
v5.274 | 2024-03-30 | Fix | F079 | BLANK SCREEN FIX: duplicate function FMT() and let G_CURRENCY= declarations removed. Root cause: new infrastructure added ON TOP of old block. Fix: replace old block in one shot from v5.273 clean base. | Dev
v5.274 | 2024-03-30 | Feature | F070 | applyFMT() engine: currency×rate, auto/manual scale, 0-4 decimals, neg style (−/parens/abs), thousands sep (Indian/Intl/none), zero display. customFmt() for Excel-style strings. | Dev
v5.274 | 2024-03-30 | Feature | F071-F073 | 6 format presets + live preview + fine controls (6 controls in 3-col grid) in Settings → Display Format. | Dev
v5.274 | 2024-03-30 | Feature | F074-F076 | Custom format string input. Editable exchange rates. SGD + GBP added (6 currencies total). | Dev
v5.274 | 2024-03-30 | Feature | F077-F078 | Header format badge replaces currency dropdown. displayFmt persisted in JSON backup. | Dev
v5.274 | 2026-04-01 | Bug | F080 | FIXED: 'displayFmt is not defined' crash in Settings — deployed file was missing displayFmt/applyDisplayFmt in SettingsPage prop signature. Redeployed from correct working file. | Dev
v5.274 | 2026-04-01 | Perf | F081 | Incremental NAV fetch: skip schemes already current, use /latest endpoint for stale schemes with existing data, full fetch only for empty schemes. Eliminates redundant downloads. | Dev
v5.275 | 2026-04-02 | Perf | F082-F084 | Separate NAV cache key (mfa_nav_v1_{user}). Parallel fetch 5 concurrent. /latest endpoint for stale schemes. ~5x faster daily refresh. | Dev
v5.275 | 2026-04-02 | Feature | F085 | RootErrorBoundary: App crashes show error message + Reload button instead of blank screen. | Dev
v5.275 | 2026-04-02 | Feature | F032,F056 | navAsOf(): Portfolio Value sub-label shows 'NAV current' or 'NAV N days old' dynamically. | Dev
v5.275 | 2026-04-02 | Fix | — | Root cause fixed: ReactDOM.class prefix on RootErrorBoundary caused Babel crash in v5.275 first attempt. Now standalone class before createRoot. | Dev
v5.276 | 2026-04-03 | Feature | F003,F005,F006,F007 | Auto-detect import: CAMS XLSX, KFintech XLSX, Generic CSV + .csv file input. parseAnyFile() routes automatically. | Dev
v5.276 | 2026-04-03 | Feature | F021 | Skip (exited) button in Scheme Mapping for zero-balance schemes. Fixed: wrapped in React Fragment to prevent adjacent JSX crash. | Dev
v5.276 | 2026-04-03 | Docs | F045-F048,F066 | Help updated: Getting Started (all formats), Settings rewritten, Display Format + Getting Help sections, Technical Glossary (12 definitions). | Dev
v5.276 | 2026-04-03 | Fix | — | Root cause of blank screen: Skip IIFE placed as 2nd child inside &&() without Fragment. Fixed with <> wrapper. | Dev
v5.277 | 2026-04-08 | Bug | F086 | FIXED: returnBasis not in DashboardPage scope. Root cause: changes applied to wrong file state. Fix: atomic 13-change patch from v5.276 clean base with 29-check verification. | Dev
v5.277 | 2026-04-08 | Feature | F087-F090 | Return basis selector: Book Cost (FIFO) / Net Deployed / Gross Invested. Toggle on Dashboard + Settings. 6 hero cards. heroStats computes all 3 gain bases every render. | Dev
v5.278 | 2026-04-12 | Feature | F091-F093 | Return basis propagated to FundOverview (Abs Return % denominator + dynamic label), fundStats (costBasis, returnPct, unrealisedGain, realizedGain per fund), FY Summary (Gain vs Net + Gain % columns). | Dev
v5.278 | 2026-04-12 | Docs | F094 | XIRR and NPV confirmed intentionally basis-independent. They use actual cash flows — not a cost basis measure. | Dev
v5.279 | 2026-04-17 | Feature | F095-F098 | Return Basis selector in global top header (Book/Net/Gross pill). Visible on every page. FYSummaryPage + AnalysisPage wired. DashboardPage prop bug fixed. | Dev
v5.280 | 2026-04-17 | Feature | F099-F100 | Portfolio Timeline chart: dashed baseline changes with basis selection (Book Cost / Net Deployed / Gross Invested). Fund Performance page: Abs Return % column added, basis-aware denominator. | Dev
v5.281 | 2026-04-17 | Feature | F004 | CAMS Current Value XLSX: parseCAMSCurrentValue() auto-detected via cams_cv format code. Seeds current holdings snapshot. | Dev
v5.281 | 2026-04-17 | Feature | F067 | Multi-portfolio system: Users → Portfolios rename throughout UI — header, modal title, add/delete/switch copy, placeholder text. | Dev
v5.282 | 2026-04-18 | Feature | F042/F101 | Multi-portfolio Compare page: ⚖ Compare tab auto-appears for 2+ portfolios. Side-by-side cards + comparison table. Loads inactive portfolios from _store. Return basis aware. | Dev
v5.283 | 2026-04-19 | Bug | F102 | FIXED: Compare page crash — COLORS not defined. Was using undefined 'COLORS' instead of module-level 'C'. | Dev
v5.283 | 2026-04-19 | Perf | F103 | Chart perf: txns pre-filtered per scheme before FIFO loop. ~180x fewer array scans per chart render. | Dev
v5.283 | 2026-04-19 | Feature | F104 | Fund Overview DataTable sort/filter toolbar now visible via title prop. | Dev
v5.283 | 2026-04-19 | Feature | F105 | Funds to Add refreshed Apr 2025: Sortino-ranked, entry-point context, AMFI codes shown for direct import. | Dev
v5.284 | 2026-04-24 | Bug | F106 | FIXED blank screen: no useMemo-in-arg, no arrow fn render props. Pre-formatted string values in DataTable columns. | Dev
v5.284 | 2026-04-24 | Feature | F107,F108 | FY Summary DataTable (sort/filter on yearly + fund tables). XIRR per-fund table (All-Time + Period XIRR sortable). | Dev
v5.285 | 2026-04-26 | Fix | F109 | Code audit: 83/84 features verified. Fixed: FundOverviewPage returnBasis missing from JSX call. Fixed: FP+Analysis prop indentation. Restored: FO DataTable title. Confirmed: DataTable has sort+filter. | Dev

## 🗺 Roadmap
MF ADVISOR — DEVELOPMENT ROADMAP
v5.273 baseline · Planned releases · Yellow cells = editable target dates
Release | Target | Theme | Feature ID | Feature | Effort | Status | Notes
v5.273 | Mar 2026 | RELEASED | — | v5.273 released: INR→FMT, filteredEnabledSet, folio separator, appendXLS, validation panel | — | Completed | All critical+high priority items done
v5.274 | Apr 2026 | Import Expansion | F003 | CAMS Transaction XLSX import | M | Pending | parseCAMSXlsxRows coded in v5.262 — re-graft onto v5.273
v5.274 | Apr 2026 | Import Expansion | F004 | CAMS Current Value XLSX import | M | Pending | parseCAMSCurrentValue coded — re-graft
v5.274 | Apr 2026 | Import Expansion | F005 | KFintech XLSX import | M | Pending | parseKFintechRows coded — re-graft
v5.274 | Apr 2026 | Import Expansion | F007 | Auto format detection | S | Pending | parseAnyFile coded — re-graft
v5.274 | Apr 2026 | Import Expansion | F021 | Skip exited funds (auto + button) | S | Pending | Coded in v5.262 — re-graft
v5.274 | Apr 2026 | NAV & UX Fixes | F032 | NAV date in portfolio value card | S | Minor Update Needed | Add navAsOf() + navDaysStale in DashboardPage
v5.274 | Apr 2026 | NAV & UX Fixes | F056 | NAV staleness date display | S | Minor Update Needed | Depends on navAsOf()
v5.274 | Apr 2026 | NAV & UX Fixes | F068 | Root-level error boundary | S | Pending | Catch App crashes gracefully
v5.274 | Apr 2026 | Docs | F045 | Update User Manual for v5.272-273 features | M | Minor Update Needed | Bulk CSV, remapping, appendXLS, validation panel
v5.275 | May 2026 | Docs & Glossary | F046 | Complete technical formula docs | L | Minor Update Needed | Sharpe, Sortino, Alpha, LTCG formulas
v5.275 | May 2026 | Docs & Glossary | F047 | Update Changelog in Help page | S | Minor Update Needed | Add v5.272-273 entries
v5.275 | May 2026 | Docs & Glossary | F066 | Link TERM_DEFS glossary from Help tab | S | Minor Update Needed
v5.275 | May 2026 | Docs & Glossary | F048 | Cross-links Help↔Settings | S | Pending
v5.276 | Jun 2026 | Portfolio System | F042 | Multi-portfolio compare page | XL | Pending | Large — ComparePortfoliosPage coded in v5.262
v5.276 | Jun 2026 | Portfolio System | F067 | Multi-portfolio system (switcher/profiles) | XL | Pending | Large — needs stable base
Backlog | TBD | Low Priority | F006 | Generic CSV import | S | Pending | Bulk upload covers most use cases